## Overview
BAForge
IMMOGEST Financial Hub Integration
Domain | EU Institutions
Description | ABAC-to-SUMMA migration for EEAS real estate management across 140+ delegations.
Version | 1.0.0
Author | SFL Consulting — Stéphane Lefort
Generated by | BAForge v3.1
PROJECT DASHBOARD
8 |  | 3 | 10 | 3 | 73
Actors |  | Workflows | Business Rules | Entities | Total Fields
5 |  | 8 | 10 | 7 | 4
API Endpoints |  | Requirements | Open Questions | TBI Fields | Gap Fields
Migration Status
ok | 62
TBI | 7
Gap | 4

## Actors
ID | Name | Type | Description | CRUD | Permissions
AC001 | HQ User Administrator | Primary Actor | Full system administration rights and user role management across all delegations | CRUD | All delegations - user management
AC002 | HQ Administrator | Primary Actor | Manage all real estate data with access to all delegations | CRUD | All delegations - full data access
AC003 | Delegation Administrator | Primary Actor | Manage delegation-specific real estate data and local user administration | CRUD | Own delegation only
AC004 | Delegation Staff (DAS) | Primary Actor | Create and manage contracts - primary IMMOGEST user for day-to-day operations | CRU | Own delegation - contracts and buildings
AC005 | Financial Hub / SUMMA | System Actor | External financial system providing LCK/LEF/BAF data via REST APIs | R | Read-only via API - no direct DB access
AC006 | ABAC Legacy System | System Actor | Legacy accrual-based accounting system being replaced by SUMMA | R | Read-only during transition period
AC007 | Auto-Expiry Scheduler | Timer/Scheduler | Automated process running at 02:01 AM to expire contracts past end date | U | Contract status updates only
AC008 | Auto-Archive Scheduler | Timer/Scheduler | Automated process running at 03:01 AM to archive buildings with contracts expired >12 months | U | Building status updates only

## Workflows
WF_ID | Name | Trigger | Owner | Step_Num | Step_Type | Step_Description | Step_Actor | Step_Output
WF001 | Contract Creation | User clicks Add Contract in building details | DAS Staff | 1 | Start | Navigate to Building Details > Contracts tab | AC004 | Contract form displayed
WF001 | Contract Creation | User clicks Add Contract in building details | DAS Staff | 2 | Action | Select contract type (Art.5/Art.23/Purchase) | AC004 | Type selected
WF001 | Contract Creation | User clicks Add Contract in building details | DAS Staff | 3 | Action | Enter LCK reference (EAS.XXXXXX format) | AC004 | LCK entered
WF001 | Contract Creation | User clicks Add Contract in building details | DAS Staff | 4 | Action | Click Pull LCK button | AC004 | API call triggered
WF001 | Contract Creation | User clicks Add Contract in building details | DAS Staff | 5 | Subprocess | System calls EP01: GET /legal-commitments/{localKey} | AC005 | LCK data retrieved
WF001 | Contract Creation | User clicks Add Contract in building details | DAS Staff | 6 | Decision | Is earlyWarning[] empty on LCK? | AC005 | Yes: continue / No: block
WF001 | Contract Creation | User clicks Add Contract in building details | DAS Staff | 7 | Subprocess | System calls EP02 + EP03 in parallel for LEF and BAF | AC005 | LEF + BAF data retrieved
WF001 | Contract Creation | User clicks Add Contract in building details | DAS Staff | 8 | Decision | Are earlyWarning[] empty on LEF AND BAF? Is BAF expiry future? | AC005 | All valid: continue / Any failed: block
WF001 | Contract Creation | User clicks Add Contract in building details | DAS Staff | 9 | Action | System populates contract fields from FH data | AC005 | Fields auto-filled
WF001 | Contract Creation | User clicks Add Contract in building details | DAS Staff | 10 | Action | User completes remaining manual fields | AC004 | All fields filled
WF001 | Contract Creation | User clicks Add Contract in building details | DAS Staff | 11 | Action | User saves contract as DRAFT | AC004 | Contract saved (DRAFT status)
WF001 | Contract Creation | User clicks Add Contract in building details | DAS Staff | 12 | End | Contract created successfully | AC004 | Audit log entry created
WF002 | LCK Pull & Validation | User clicks Pull LCK button on contract form | System | 1 | Start | User enters LCK reference | AC004 | LCK reference entered
WF002 | LCK Pull & Validation | User clicks Pull LCK button on contract form | System | 2 | Decision | Is LCK format valid (EAS.XXXXXX)? | AC005 | Valid: proceed / Invalid: show BR064 error
WF002 | LCK Pull & Validation | User clicks Pull LCK button on contract form | System | 3 | Subprocess | Call GET /legal-commitments/{localKey}/last-validated | AC005 | HTTP response received
WF002 | LCK Pull & Validation | User clicks Pull LCK button on contract form | System | 4 | Decision | HTTP 200? LCK found? | AC005 | 200: proceed / 404: Not found / 500: ABAC unreachable
WF002 | LCK Pull & Validation | User clicks Pull LCK button on contract form | System | 5 | Decision | Is classification_category == BUILDING? | AC005 | Yes: proceed / No: Wrong category error
WF002 | LCK Pull & Validation | User clicks Pull LCK button on contract form | System | 6 | Decision | Is LCK already used by another contract? | AC005 | No: proceed / Yes: Already in use error
WF002 | LCK Pull & Validation | User clicks Pull LCK button on contract form | System | 7 | Action | Extract contractors[].legal_entity_local_key and bank_account_local_key | AC005 | LEF + BAF keys extracted
WF002 | LCK Pull & Validation | User clicks Pull LCK button on contract form | System | 8 | End | LCK validation complete - trigger LEF + BAF calls | AC005 | Ready for EP02 + EP03
WF003 | Contract Amendment | User clicks Add Amendment on In Force contract | DAS Staff | 1 | Start | Open In Force contract details | AC004 | Amendment option available
WF003 | Contract Amendment | User clicks Add Amendment on In Force contract | DAS Staff | 2 | Decision | Is contract status IN_FORCE? | AC005 | Yes: allow amendment / No: block
WF003 | Contract Amendment | User clicks Add Amendment on In Force contract | DAS Staff | 3 | Action | System creates new version linked to original LCK | AC005 | Amendment draft created with change_request_type
WF003 | Contract Amendment | User clicks Add Amendment on In Force contract | DAS Staff | 4 | Action | User modifies allowed fields (amounts dates) | AC004 | Fields updated
WF003 | Contract Amendment | User clicks Add Amendment on In Force contract | DAS Staff | 5 | Action | User submits amendment for approval | AC004 | Amendment submitted
WF003 | Contract Amendment | User clicks Add Amendment on In Force contract | DAS Staff | 6 | End | Amendment saved and linked to original contract | AC004 | Audit trail updated

## Business Rules
ID | Name | Category | Priority | Condition | Action | Exception | Source | RelatedReq
BR003 | Contract Status Lifecycle | Workflow | Critical | Contract status changes requested | Enforce valid transitions: DRAFT > IN_FORCE > EXPIRED > ARCHIVED | Reject invalid transition and log attempt | IMMOGEST spec v2 | REQ-001
BR006 | Contract Type Validation | Validation | High | User selects contract type | Validate against allowed types: Art.5 Lease / Art.23 Lease / Purchase / Sub-lease / Administrative | Show error: Invalid contract type | IMMOGEST spec v2 | REQ-002
BR049 | Delete Building Guard | Authorization | Critical | User attempts to delete building | Allow deletion ONLY if no contracts exist including DRAFT status | Show error: Cannot delete building with existing contracts | IMMOGEST spec v2 | REQ-015
BR050 | Delete Contract Guard | Authorization | High | User attempts to delete contract | Allow deletion ONLY for DRAFT status contracts | Show error: Only draft contracts can be deleted | IMMOGEST spec v2 | REQ-016
BR053 | LCK Format Validation | Validation | Critical | LCK reference entered by user | Validate format: three letters + dot + six digits (e.g. EAS.123456) | Show error messages per BR064 | Financial Hub spec | REQ-003
BR054 | Single In Force Contract | Workflow | Critical | Contract activation requested | Only one contract with status IN_FORCE allowed per building at any time | Show error: Another contract is already In Force for this building | IMMOGEST spec v2 | REQ-004
BR055 | BAF Validation | Compliance | Critical | Bank account data retrieved from Financial Hub | IBAN format check + central_status must be VALID + workflow_status must be VALID | Block contract creation and show specific validation error | Financial Hub spec | REQ-005
BR060 | Automatic Expiry Process | Workflow | High | System clock reaches 02:01 AM daily | Check all IN_FORCE contracts - if end_date < today then set status to EXPIRED | Log failed expiry attempts for manual review | IMMOGEST spec v2 | REQ-006
BR064 | LCK Validation Messages | Validation | High | LCK validation fails | Display specific error: Empty LCK / Not found in LCK / ABAC unreachable / Wrong category / Expired / Already in use | Log all validation failures with timestamp and user | Financial Hub spec | REQ-003
BR067 | Supported File Types | Validation | Medium | User uploads document | Validate against whitelist: jpg jpeg jfif png pdf doc docx xls xlsx ppt pps pptx rtf txt gif bmp zip 7z xsl kml kmz msg tif dwg | Show error: File type not supported | IMMOGEST spec v2 | REQ-020

## LCK Fields
Legal Commitment (LCK): 38 fields ¦ 31 ok ¦ 7 TBI ¦ 0 Gap
Field_Name | Label | Source_Path | Target_Field | Data_Type | Edit_Mode | Mandatory | BR_Ref | Sample_Value | Migration_Status | Compliance_Note
local_key | LCK Reference | local_key | lck_reference | String | Read | Y | BR053 | EAS.517864 | ok
central_identifier | Central Identifier | central_identifier | central_id | String | Read | N |  | LC-02915910 | ok
display_key | Display Key | display_key | display_key | String | Read | N |  | LC-02915910 | ok
legal_commitment_type | Commitment Type | legal_commitment_type | commitment_type | String | Read | Y |  | GLOBAL | ok
classification_category | Category | classification_category | classification_cat | String | Read | Y | BR052 | BUILDING | ok | Must be BUILDING
multi_annual_flag | Multi-Annual | multi_annual_flag | multi_annual | Boolean | Read | N |  | true | ok
contract_amount | Contract Amount | amounts.contract_amount.value | contract_amount | Decimal | Read | Y |  | 125000.00 | ok
contract_currency | Currency | amounts.contract_amount.currency | contract_currency | String | Read | Y |  | EUR | ok
instalment_amount | Instalment Amount | amounts.instalment_amount.value | instalment_amount | Decimal | Read | N |  | 10416.67 | ok
covered_amount | Covered Amount | amounts.covered_amount.value | covered_amount | Decimal | Read | N |  | 125000.00 | ok
signature_date | Signature Date | dates.signature_date | signature_date | Date | Read | N |  | 2023-06-15 | ok
in_force_date | In Force Date | dates.in_force_date | in_force_date | Date | Read | N |  | 2023-07-01 | ok
start_date | Start Date | dates.start_date | start_date | Date | Read | Y |  | 2023-07-01 | ok
end_date | End Date | dates.end_date | end_date | Date | Read | Y |  | 2026-06-30 | ok
closing_date | Closing Date | dates.closing_date | closing_date | Date | Read | N |  |  | ok
amendment_type_code | Amendment Type | amendment_type_code | amendment_type | String | Read | N |  | ORIGINAL | ok
change_request_type | Change Request Type | change_request_type_code | change_request_type | String | Read | N | BR055 |  | ok
root_status | Root Status | root_status | root_status | String | Read | Y |  | ESTABLISHED | ok
workflow_status | Workflow Status | workflow_info.workflow_status | workflow_status | String | Read | Y |  | VALID | ok
workflow_org | Workflow Org | workflow_info.current_workflow_organisation | workflow_org | String | Read | N |  | EEAS | ok
central_status | Central Status | workflow_info.central_references[].central_status | central_status | String | Read | Y |  | VALID | ok
contractor_lef_key | Contractor LEF Key | contractors[].legal_entity_local_key | contractor_lef | String | Read | Y |  | 6000807055 | ok | Triggers LEF API call
contractor_baf_key | Contractor BAF Key | contractors[].bank_account_local_key | contractor_baf | String | Read | Y |  | 0003030047 | ok | Triggers BAF API call
commitment_bcl_keys | Budget Commitment Keys | commitment_local_keys[] | bcl_keys | Array | Read | N |  |  | ok
indexation_flag | Indexation Flag | indexation_flag | indexation_flag | Boolean | Read | N |  | false | ok
notice_period | Notice Period | N/A | notice_period | Integer | Edit | N |  |  | TBI | Not found in FH response
deposit_amount | Deposit Amount | N/A | deposit_amount | Decimal | Edit | N |  |  | TBI | Not found in FH response
deposit_type | Deposit Type | N/A | deposit_type | String | Edit | N |  |  | TBI | Not found in FH response
agency_fees | Agency Fees | N/A | agency_fees | Decimal | Edit | N |  |  | TBI | Not found in FH response
charges_amount | Charges Amount | N/A | charges_amount | Decimal | Edit | N |  |  | TBI | Separate from rent - not identified in FH
land_plot_value | Land Plot Value | N/A | land_plot_value | Decimal | Edit | N |  |  | TBI | Purchase-specific - not found in FH
gifted_status | Gifted Status | N/A | gifted_flag | Boolean | Edit | N |  |  | TBI | Purchase-specific flag missing
early_warning | Early Warning | earlyWarning[] | early_warning | Array | Read | Y | BR055 | [] | ok | MUST BE EMPTY for contract to proceed
warning_type | Warning Type | earlyWarning[].type | warning_type | String | Read | N |  |  | ok | Sanction type code
warning_desc | Warning Description | earlyWarning[].description | warning_desc | String | Read | N |  |  | ok
responsible_org | Responsible Org | responsible_organisation.name | responsible_org | String | Read | N |  | EEAS | ok
audit_creation_date | Created Date | audit_info.creation_date | created_date | DateTime | Read | N |  | 2023-06-01T10:30:00 | ok | Audit trail
audit_modification_date | Modified Date | audit_info.modification_date | modified_date | DateTime | Read | N |  | 2024-01-15T14:22:00 | ok | Audit trail

## LEF Fields
Legal Entity (LEF): 20 fields ¦ 18 ok ¦ 0 TBI ¦ 2 Gap
Field_Name | Label | Source_Path | Target_Field | Data_Type | Edit_Mode | Mandatory | BR_Ref | Sample_Value | Migration_Status | Compliance_Note
lef_local_key | LEF Reference | local_key | lef_reference | String | Read | Y | BR054 | 6000740916 | ok
lef_type | Entity Type | _type | entity_type | String | Read | Y | BR054 | PrivatePersonR | ok | Polymorphic: PrivatePersonR/PublicLawBodyR/PrivateLawBodyR/StaffMemberR
lef_account_group | Account Group | account_group_code | account_group | String | Read | N |  | LE09 | ok
lef_language | Language | language_code | language | String | Read | N |  | EN | ok
lef_name | Full Name | name | landlord_name | String | Read | Y |  | TEODORESCU LOREDANA CAROLINA | ok | GDPR - personal data
lef_first_name | First Name | first_name | first_name | String | Read | N |  | LOREDANA CAROLINA | ok | GDPR
lef_last_name | Last Name | last_name | last_name | String | Read | N |  | TEODORESCU | ok | GDPR
lef_country | Country | country_code | country | String | Read | N |  | IT | ok
lef_address_street | Street | official_address.street | address_street | String | Read | N |  | Via Roma 42 | ok
lef_address_city | City | official_address.city | address_city | String | Read | N |  | Milano | ok
lef_address_postal | Postal Code | official_address.postal_code | address_postal | String | Read | N |  | 20121 | ok
lef_national_id | National ID | national_id_number | national_id | String | Read | N |  | YB1814155 | ok | GDPR - sensitive
lef_passport | Passport | passport.number | passport_number | String | Read | N |  |  | ok | GDPR - sensitive
lef_early_warning | Early Warning | earlyWarning[] | lef_early_warning | Array | Read | Y | BR054 | [] | ok | MUST BE EMPTY
lef_central_status | Central Status | workflow_info.central_references[].central_status | lef_central_status | String | Read | Y | BR054 | VALID | ok | Must be VALID
lef_workflow_status | Workflow Status | workflow_info.workflow_status | lef_workflow_status | String | Read | Y |  | VALID | ok
lef_mailing_address | Mailing Address | mailingAddress | lef_mailing | Object | Read | N |  |  | N/A | Not needed for contracts - can be dropped
lef_original_key | Original Local Key | originalLocalKey | lef_original_key | String | Read | N |  |  | N/A | Pre-migration key - likely not needed
lef_responsible_user | Responsible User | responsibleUser | lef_responsible | Object | Read | N |  |  | Gap | Not in FH response - display only
lef_supporting_docs | Supporting Documents | supportingDocumentFolder | lef_supporting | Object | Read | N |  |  | Gap | Not in FH response

## BAF Fields
Bank Account (BAF): 15 fields ¦ 13 ok ¦ 0 TBI ¦ 2 Gap
Field_Name | Label | Source_Path | Target_Field | Data_Type | Edit_Mode | Mandatory | BR_Ref | Sample_Value | Migration_Status | Compliance_Note
baf_local_key | BAF Reference | local_key | baf_reference | String | Read | Y | BR055 | 0003030047 | ok
baf_iban | IBAN | iban | iban | String | Read | Y | BR055 | IT60X0542811101000000123456 | ok | GDPR - must be masked in UI
baf_bic | BIC/SWIFT | bic | bic | String | Read | N |  | BPMOIT22XXX | ok
baf_account_name | Account Holder | account_name | account_holder | String | Read | Y |  | TEODORESCU LOREDANA CAROLINA | ok | GDPR
baf_currency | Currency | currency_code | baf_currency | String | Read | N |  | EUR | ok
baf_country | Country | country_code | baf_country | String | Read | N |  | IT | ok
baf_expiry_date | Expiry Date | expiry_date | baf_expiry | Date | Read | Y | BR055 | 2027-12-31 | ok | MUST be in the future
baf_early_warning | Early Warning | earlyWarning[] | baf_early_warning | Array | Read | Y | BR055 | [] | ok | MUST BE EMPTY
baf_central_status | Central Status | workflow_info.central_references[].central_status | baf_central_status | String | Read | Y | BR055 | VALID | ok | Must be VALID
baf_workflow_status | Workflow Status | workflow_info.workflow_status | baf_workflow_status | String | Read | Y |  | VALID | ok
baf_linked_lef_key | Linked LEF Key | /bank-accounts/{key}/legal-entities.[].legal_entity_local_key | baf_lef_key | String | Read | N |  | 6000735326 | ok | Sub-endpoint cross-reference
baf_linked_lef_status | Linked LEF Status | /bank-accounts/{key}/legal-entities.[].status_code | baf_lef_status | String | Read | N |  | VALID | ok
baf_ares_document | ARES Document | ares_document | baf_ares | Object | Read | N |  |  | Partial | Available in BAF but may be empty for test entity
baf_responsible_user | Responsible User | responsibleUser | baf_responsible | Object | Read | N |  |  | Gap | Not in FH response - display only
baf_supporting_docs | Supporting Documents | supportingDocumentFolder | baf_supporting | Object | Read | N |  |  | Gap | Not in FH response

## API Endpoints
ID | Method | Path | Description | Entity | Call_Sequence | Rate_Limiting | Request_Sample | Response_Sample
EP01 | GET | /legal-commitments/{localKey}/last-validated | Retrieve legal commitment data by local key | LCK | 1. Call with LCK reference from user input. 2. Extract contractors[].legal_entity_local_key and bank_account_local_key. 3. Trigger EP02 + EP03 in parallel. | OAuth 2.0 Bearer token. 100 req/min. Circuit breaker after 5 consecutive failures. | {"local_key": "EAS.517864"} | {"local_key": "EAS.517864" "contractors": [{"legal_entity_local_key": "6000807055" "bank_account_local_key": "0003030047"}]}
EP02 | GET | /legal-entities/{localKey} | Retrieve legal entity (landlord) data | LEF | Called after EP01 returns contractor keys. Extract _type to determine polymorphic structure (PrivatePersonR/PublicLawBodyR/PrivateLawBodyR/StaffMemberR). | OAuth 2.0. Same token as EP01. | {"local_key": "6000807055"} | {"local_key": "6000807055" "_type": "PrivatePersonR" "name": "TEODORESCU LOREDANA CAROLINA" "earlyWarning": []}
EP03 | GET | /bank-accounts/{localKey} | Retrieve bank account data for payment | BAF | Called in parallel with EP02 after EP01. Validate IBAN format + expiry_date must be future + earlyWarning[] must be empty. | OAuth 2.0. IBAN must be masked in logs. | {"local_key": "0003030047"} | {"local_key": "0003030047" "iban": "IT60X054281..." "expiry_date": "2027-12-31" "earlyWarning": []}
EP04 | GET | /budget-commitments/{localKey} | Retrieve budget commitment line data | BCL | Called optionally from commitment_local_keys[] in EP01 response. Used for budget validation. | OAuth 2.0. Read-only. | {"local_key": "BCL-12345"} | {"local_key": "BCL-12345" "budget_line": "A-3000" "amount": 125000}
EP05 | GET | /bank-accounts/{localKey}/legal-entities | Retrieve legal entities linked to a bank account | BAF-LEF | Sub-endpoint of EP03. Cross-references BAF to LEF. Used for validation that BAF holder matches contract landlord. | OAuth 2.0. | {"local_key": "0003030047"} | [{"legal_entity_local_key": "6000735326" "status_code": "VALID"}]

## Traceability
Req_ID | Requirement | User_Story | Test_Case | Test_Steps | Priority | Status
REQ-001 | System shall enforce valid contract status transitions (DRAFT > IN_FORCE > EXPIRED > ARCHIVED) | As a DAS user I want the system to prevent invalid status changes so that contract integrity is maintained | TC-001 | Given a DRAFT contract When user attempts to set status to ARCHIVED Then system rejects with error message | Critical | Approved
REQ-002 | System shall validate contract type against allowed types (Art.5/Art.23/Purchase/Sub-lease/Administrative) | As a DAS user I want to select from valid contract types so that contracts are properly classified | TC-002 | Given contract creation form When user selects type Then only valid options are available | High | Approved
REQ-003 | System shall validate LCK reference format as EAS.XXXXXX (3 letters + dot + 6 digits) | As a DAS user I want immediate LCK format validation so that I get clear feedback before calling Financial Hub | TC-003 | Given LCK input field When user enters EAS-123456 (wrong format) Then system shows format error before API call | Critical | Implemented
REQ-004 | System shall enforce maximum one IN_FORCE contract per building at any time | As a system administrator I want single active contract enforcement so that financial data remains consistent | TC-004 | Given building with IN_FORCE contract When user attempts to activate second contract Then system blocks activation | Critical | Approved
REQ-005 | System shall validate BAF data: IBAN format + central_status VALID + earlyWarning[] empty + expiry_date future | As a DAS user I want automatic bank account validation so that payments go to verified accounts | TC-005 | Given BAF with expired date When system retrieves BAF data Then contract creation is blocked with expiry warning | Critical | In Progress
REQ-006 | System shall automatically expire contracts at 02:01 AM when end_date passes current date | As a system I want automatic expiry so that contract statuses remain accurate without manual intervention | TC-006 | Given IN_FORCE contract with end_date yesterday When scheduler runs at 02:01 Then status changes to EXPIRED | High | Tested
REQ-007 | System shall call Financial Hub APIs in correct sequence: LCK first then LEF+BAF in parallel | As a developer I want clear API call sequencing so that data dependencies are respected | TC-007 | Given user clicks Pull LCK When system processes Then EP01 completes before EP02+EP03 start in parallel | High | Draft
REQ-008 | System shall mask IBAN in all UI displays and logs showing only last 4 digits | As a data protection officer I want IBAN masking so that we comply with GDPR data minimisation | TC-008 | Given BAF data displayed When user views contract details Then IBAN shows as XXXX...3456 | Critical | Draft

## Open Questions
ID | Question | Context | Entity_Field | Priority | Status | Assigned_To | Answer
Q001 | Will the EAS.XXXXXX LCK format be preserved in SUMMA? | Currently ABAC uses EAS.XXXXXX. If SUMMA changes the format the validation rules must be updated | LCK.local_key | Critical | Open | SUMMA Team
Q002 | Does Financial Hub expose earlyWarning[] for LEF entities? | Test entity 6000740916 returned empty array but need confirmation it exists for all entity types | LEF.earlyWarning | High | Open | Integration Team
Q003 | What are the exact workflow status codes mapping to IMMOGEST states? | IMMOGEST uses DRAFT/IN_FORCE/EXPIRED/ARCHIVED. Need SUMMA equivalent codes | LCK.workflow_status | High | Blocked | SUMMA Team
Q004 | How should IMMOGEST handle the complex CRU objects (currency/organisation/contractor)? | Financial Hub returns nested objects. Need to determine if we flatten or store as JSON | LCK.contractors[] | Medium | Open | Architecture Team
Q005 | What HTTP error codes will Financial Hub return for each validation scenario? | Need exact codes for: not found / expired / wrong category / already used / server error | API.error_codes | High | Open | Integration Team
Q006 | Is the BAF expiry_date field always populated? | Some test entities returned null expiry. Need to know if this is optional or mandatory | BAF.expiry_date | High | Open | SUMMA Team
Q007 | Will EEAS Connect replace current OAuth for Financial Hub authentication? | Migration from current auth to EEAS Connect (OAuth 2.0/OIDC) timing unclear | API.authentication | Medium | Open | Security Team
Q008 | What is the cutover model: big-bang or phased? | ~500 active contracts across ~140 delegations need to transition. Phased recommended | Migration.cutover | Critical | Open | Project Sponsor
Q009 | Are LCK references identical in ABAC and SUMMA? | If not a mapping table is needed before cutover | LCK.local_key | Critical | Open | SUMMA Team
Q010 | What happens to DRAFT/WAH contracts during cutover? | Must be completed or cancelled. Freeze period needed | Migration.in_flight | High | Open | Project Manager

## Glossary
Term | Definition | Related_Entity
ABAC | Accrual-Based Accounting system. EU legacy financial system being replaced by SUMMA. | LCK
ARES | Advanced Records System. EU document management. Referenced in BAF for bank certificates. | BAF
Art.5 | Article 5 of Staff Regulations. Short-term lease below financial threshold. | LCK
Art.23 | Article 23 of Financial Regulation. Long-term lease requiring HoA approval. | LCK
BAF | Bank Account File. SUMMA entity: validated bank account (IBAN BIC holder). | BAF
BCL | Budget Commitment Line. SUMMA entity: annual budget allocation linked to an LCK. | LCK
BIC | Bank Identifier Code (SWIFT code). 8 or 11 character code identifying a bank. | BAF
BR | Business Rule. Numbered BRxxx. See Business Rules Catalog.
DAS | Delegation Administrative Support. Primary IMMOGEST user who creates and manages contracts.
EEAS | European External Action Service. EU diplomatic service operating 140+ delegations worldwide.
EEAS Connect | Expected OAuth 2.0 / OIDC authentication service for EEAS applications. To be confirmed.
FH | Financial Hub. SUMMA integration layer exposing Business Partner APIs. | LCK/LEF/BAF
HoA | Head of Administration. Approver for Art.23 contracts.
IBAN | International Bank Account Number. Must be masked per GDPR. | BAF
IMMOGEST | External Service Real Estate management system for EEAS delegations.
LEF | Legal Entity File. SUMMA entity: landlord identity (name address type sanctions). | LEF
LCK | Legal Commitment Key. SUMMA entity: contract financial commitment. | LCK
SUMMA | EU next-generation financial management system replacing ABAC. | LCK/LEF/BAF
WAH | Waiting for Approval by HoA. Contract workflow status. | LCK
WAS | Waiting for Approval by Supervisor. Contract workflow status. | LCK

## Cross-References
Cross-Reference Map
Shows all links between actors, workflows, rules, fields, requirements, and endpoints
Source Type | Source ID | Link Type | Target Type | Target ID | Context
Workflow | WF001 | uses actor | Actor | AC004 | DAS Staff creates contracts (steps 1-4, 10-12)
Workflow | WF001 | uses actor | Actor | AC005 | Financial Hub provides data (steps 5-9)
Workflow | WF001 | triggers rule | Rule | BR053 | LCK format validated at step 3
Workflow | WF001 | triggers rule | Rule | BR055 | BAF validation at step 8
Workflow | WF002 | triggers rule | Rule | BR064 | LCK error messages at steps 2-6
Rule | BR003 | implements | Requirement | REQ-001 | Contract status lifecycle enforcement
Rule | BR053 | implements | Requirement | REQ-003 | LCK format validation EAS.XXXXXX
Rule | BR053 | validates field | Field | LCK.local_key | Format check before API call
Rule | BR055 | implements | Requirement | REQ-005 | BAF IBAN + status + warning validation
Rule | BR055 | validates field | Field | LCK.early_warning | earlyWarning[] must be empty
Rule | BR055 | validates field | Field | BAF.baf_iban | IBAN format check
Rule | BR060 | implements | Requirement | REQ-006 | Auto-expiry at 02:01 AM
Rule | BR060 | reads field | Field | LCK.end_date | Compares end_date with current date
Endpoint | EP01 | returns data for | Entity | LCK | GET /legal-commitments/{localKey}
Endpoint | EP01 | triggers | Endpoint | EP02+EP03 | Extracts LEF + BAF keys from contractors[]
Endpoint | EP03 | enforces | Rule | BR055 | BAF validation on API response
Requirement | REQ-003 | tested by | Test Case | TC-003 | Given invalid LCK format Then error shown
Requirement | REQ-005 | tested by | Test Case | TC-005 | Given expired BAF Then contract blocked
Field | LCK.notice_period | status: TBI | Source | N/A | Not found in Financial Hub response
Field | LEF.lef_responsible_user | status: Gap | Source | N/A | Not in FH response — display-only field

## RACI Matrix
RACI Matrix
R = Responsible (does the work) ¦ A = Accountable (owns the outcome) ¦ C = Consulted (provides input) ¦ I = Informed (kept updated)
Deliverable / Activity | HQ User Admin | HQ Admin | Deleg Admin | DAS Staff | Financial Hub | ABAC Legacy | Auto-Expiry | Auto-Archive
Project charter | I | A |  | C
Stakeholder analysis |  | R | C | C
As-Is documentation |  | A |  | R |  | C
To-Be architecture |  | A |  |  | C
Business rules catalogue |  | A |  | R
Field mapping document |  | A |  | R | C
API integration specs |  | A |  |  | R
Compliance assessment | R | A
Test strategy |  | A |  | R
UAT execution |  | A | R | R
Cutover plan |  | A |  |  | C | C
Training delivery |  | R | I | I
Go-live decision | A | R | C
Hypercare support |  | R | R | I

## Risk Register
Risk Register
Risk ID | Description | Category | Probability (1-5) | Impact (1-5) | Score | Mitigation | Owner | Status | Linked REQ
RSK-001 | Financial Hub API response structure differs from ABAC flat files requiring extensive mapping rework | Integration | 4 | 4 |  | Build adapter layer. Validate mapping against test data from FH sandbox. Maintain ABAC fallback for 3 months. | Integration Lead | Mitigating | REQ-007
RSK-002 | 7 contract fields (notice_period, deposits, agency_fees) not available in Financial Hub | Data Quality | 5 | 3 |  | Confirm with SUMMA team. If not available: manual entry fields with validation. Track as TBI. | BA Lead | Open
RSK-003 | 140+ delegations must transition without service interruption during cutover | Operational | 3 | 5 |  | Phased rollout by region (5 waves). Parallel run period of 2 weeks per wave. Rollback procedure tested. | Project Manager | Open
RSK-004 | No Financial Hub sandbox environment available for integration testing | Technical | 4 | 4 |  | Request sandbox from DG BUDG. If unavailable: build mock service from API specs. Record/replay pattern. | Integration Lead | Escalated | REQ-007
RSK-005 | ABAC decommission deadline creates hard cutover pressure with no extension possible | External | 5 | 5 |  | Negotiate grace period. Identify minimum viable scope for phase 1. Contingency: direct DB migration without FH. | Project Sponsor | Open
RSK-006 | GDPR-sensitive fields (IBAN, landlord name, national ID) require encryption and masking not yet implemented | Regulatory | 3 | 4 |  | Implement IBAN masking (show last 4 digits). Encrypt at rest. DPIA before go-live. | Security Officer | Mitigating | REQ-008

## NFRs
Non-Functional Requirements
NFR ID | Category | Requirement | Metric | Target | Measurement Method | Priority | Linked Entity
NFR-001 | Performance | LCK pull operation (EP01 + EP02 + EP03) must complete within 3 seconds end-to-end | Response time (p95) | < 3,000 ms | APM monitoring on production. Load test with 50 concurrent users. | Critical | LCK
NFR-002 | Availability | IMMOGEST must be available 99.5% during business hours (07:00-19:00 CET) excluding planned maintenance | Uptime percentage | > 99.5% | Synthetic monitoring. Monthly SLA report. | High
NFR-003 | Security | IBAN must be encrypted at rest (AES-256) and masked in all UI displays and logs | Encryption coverage | 100% of IBAN fields | Security scan. Penetration test. Log audit. | Critical | BAF
NFR-004 | Scalability | System must support 140 delegations with up to 10 concurrent contract creation flows per delegation | Concurrent users | 1,400 simultaneous | Load test simulating peak usage across all delegations. | High
NFR-005 | Disaster Recovery | Recovery Point Objective (RPO) of 1 hour and Recovery Time Objective (RTO) of 4 hours | RPO / RTO | RPO < 1h, RTO < 4h | Annual DR drill. Backup verification. | High
NFR-006 | Compliance | Full audit trail for all contract status changes including user, timestamp, old value, new value | Audit completeness | 100% of state changes logged | Audit log review. ISAE 3402 assessment. | Critical | LCK

## Assumptions
Assumptions & Dependencies
ID | Type | Description | Impact if Wrong | Validated | Owner | Date | Linked Risk
A-001 | Assumption | Financial Hub will expose earlyWarning[] for all three entity types (LCK, LEF, BAF) | If not: cannot validate sanctions status. Manual check required per contract. | Pending | Integration Team | 2026-01-20 | RSK-002
A-002 | Assumption | EAS.XXXXXX LCK format will be preserved in SUMMA (not changed during migration) | If changed: all validation rules (BR053, BR064) must be updated. Existing contracts need key remapping. | Pending | SUMMA Team | 2026-01-15
A-003 | Dependency | DG BUDG must provide Financial Hub sandbox environment by Q2 2026 | If delayed: integration testing blocked. Mock services extend timeline by 4-6 weeks. | No | Project Manager | 2026-02-01 | RSK-004
A-004 | Dependency | EU Login / EEAS Connect OAuth 2.0 tokens will work with Financial Hub endpoints | If not: separate authentication mechanism needed. Security review adds 3-4 weeks. | Pending | Security Team | 2026-03-01
A-005 | Constraint | No changes to IMMOGEST data model allowed — only integration layer additions | Limits how TBI fields can be stored. May require extension tables. | Yes | Architecture Board | 2025-12-15
A-006 | Assumption | All ~500 active contracts will have valid LCK references in SUMMA at cutover time | If not: orphaned contracts with no financial data. Manual reconciliation for each. | No | SUMMA Team | 2026-02-15 | RSK-005

## Decision Log
Decision Log
ID | Decision | Rationale | Alternatives Considered | Decided By | Date | Status | Linked REQ/BR
DEC-001 | Use asynchronous API call pattern: LCK first, then LEF + BAF in parallel | Reduces total response time from ~9s (sequential) to ~5s. LEF and BAF are independent. | 1. Sequential (simpler but slower). 2. Fully parallel (complex, LCK must be first for key extraction). | Architecture Board | 2026-01-10 | Approved | REQ-007
DEC-002 | Store TBI fields (notice_period, deposits) as IMMOGEST-local data with manual entry | Financial Hub does not expose these fields. No timeline for SUMMA to add them. | 1. Wait for SUMMA enhancement (blocks project). 2. Drop fields (business rejects). | Project Sponsor | 2026-01-25 | Approved | RSK-002
DEC-003 | Phased cutover by region (5 waves of ~28 delegations each) | Big-bang too risky for 140 delegations. Phased allows learning and rollback per wave. | 1. Big-bang (faster but high risk). 2. Individual delegation (too slow, 140 deployments). | Steering Committee | 2026-02-15 | Proposed | RSK-003
DEC-004 | Mask IBAN showing only last 4 digits in all UI and log outputs | GDPR data minimisation. Full IBAN only needed for payment processing (backend). | 1. Show full IBAN with role-based access (complex RBAC). 2. No display at all (business rejects). | DPO + Security Officer | 2026-01-30 | Approved | REQ-008, BR055

## Data Volumes
Data Volume & Sizing Estimates
Entity | Current Rows | Annual Growth % | Projected at Go-Live | Peak Concurrent Users | API Calls/Min (Peak) | Avg Record Size (KB) | Total Storage (GB) | SLA Target
Legal Commitments (LCK) | 12000 | 8 |  | 200 | 50 | 4.2 |  | < 3s response time (EP01)
Legal Entities (LEF) | 8500 | 5 |  | 200 | 50 | 2.8 |  | < 2s response time (EP02)
Bank Accounts (BAF) | 9200 | 5 |  | 200 | 50 | 1.5 |  | < 2s response time (EP03)
Contracts (IMMOGEST) | 4800 | 10 |  | 500 | 20 | 8.5 |  | < 1s local operations
Buildings (IMMOGEST) | 3200 | 3 |  | 500 | 10 | 6 |  | < 1s local operations
Documents (ARES) | 25000 | 15 |  | 300 | 5 | 250 |  | < 5s retrieval
TOTAL

## Change Requests
Change Request Register
CR ID | Title | Description | Requestor | Date | Impact | Effort (days) | Affected REQs | Affected Fields | Status | Approved By
CR-001 | Add deposit_amount field to LCK entity | Business requires tracking deposit amounts per contract. Field not in Financial Hub — store locally with manual entry. | Real Estate Unit | 2026-02-20 | Medium | 3 | REQ-002 | LCK.deposit_amount | Approved | Project Sponsor
CR-002 | Extend BAF validation to include BIC code check | Audit team requires BIC validation alongside IBAN. New business rule BR066. | Internal Audit | 2026-03-05 | Low | 2 | REQ-005 | BAF.baf_bic | Assessing
CR-003 | Add agency_fees field to contract form | Agency fees tracked in ABAC but not exposed by Financial Hub. Local field with approval workflow. | Budget Unit | 2026-03-10 | Medium | 5 | REQ-002 | LCK.agency_fees | Submitted