## Overview
BAForge
IFRS 17 Implementation
Domain | Insurance
Description | Actuarial engine integration with GL posting and Solvency II parallel run.
Version | 1.0.0
Author | SFL Consulting — Stéphane Lefort
Generated by | BAForge v3.1
PROJECT DASHBOARD
8 |  | 2 | 8 | 1 | 19
Actors |  | Workflows | Business Rules | Entities | Total Fields
6 |  | 2 | 2
Requirements |  | TBI Fields | Gap Fields
Migration Status
ok | 15
TBI | 2
Gap | 2

## Actors
ID | Name | Type | Description | CRUD | Permissions
AC001 | Chief Actuary | Primary Actor | Owns IFRS 17 measurement models and assumption setting | RU | All contract groups and CSM calculations
AC002 | Finance Controller | Primary Actor | Manages P&L impact and regulatory reporting (Pillar 3) | CRUD | Financial statements and disclosures
AC003 | Claims Handler | Primary Actor | Processes claims and updates incurred claims reserves | CRU | Claims records and reserve adjustments
AC004 | Underwriting System | System Actor | Policy administration - creates and manages insurance contracts | CRUD | Policy lifecycle and premium data
AC005 | Actuarial Engine (Prophet/IFRS) | System Actor | Calculates BEL cashflows CSM amortisation and risk adjustment | CRU | Actuarial models and output datasets
AC006 | GL / Subledger | System Actor | General Ledger receiving IFRS 17 journal entries | CU | Chart of accounts and postings
AC007 | Solvency II Engine | System Actor | Parallel regulatory capital calculation under Solvency II | R | SCR/MCR data feeds
AC008 | Quarterly Close Scheduler | Timer/Scheduler | Triggers IFRS 17 closing process on last business day of quarter | U | Locks periods and triggers calculations

## Workflows
WF_ID | Name | Trigger | Owner | Step_Num | Step_Type | Step_Description | Step_Actor | Step_Output
WF001 | Quarterly IFRS 17 Close | Quarter-end close scheduler fires | AC002 | 1 | Start | Lock underwriting period - no new policies backdated | AC008 | Period locked
WF001 | Quarterly IFRS 17 Close | Quarter-end close scheduler fires | AC002 | 2 | Action | Extract policy and claims data from underwriting system | AC004 | Raw data extract
WF001 | Quarterly IFRS 17 Close | Quarter-end close scheduler fires | AC002 | 3 | Subprocess | Run actuarial engine: BEL cashflows + risk adjustment per BR001 | AC005 | Actuarial output dataset
WF001 | Quarterly IFRS 17 Close | Quarter-end close scheduler fires | AC002 | 4 | Decision | Are assumption changes required this quarter? (BR003) | AC001 | Yes: update + rerun / No: proceed
WF001 | Quarterly IFRS 17 Close | Quarter-end close scheduler fires | AC002 | 5 | Action | Calculate CSM amortisation based on coverage units per BR002 | AC005 | CSM movement schedule
WF001 | Quarterly IFRS 17 Close | Quarter-end close scheduler fires | AC002 | 6 | Action | Generate IFRS 17 journal entries for GL posting | AC005 | Journal entries file
WF001 | Quarterly IFRS 17 Close | Quarter-end close scheduler fires | AC002 | 7 | Subprocess | Post journals to subledger and reconcile with GL | AC006 | GL balanced
WF001 | Quarterly IFRS 17 Close | Quarter-end close scheduler fires | AC002 | 8 | Action | Produce IFRS 17 disclosures and Pillar 3 reports | AC002 | Disclosure pack
WF001 | Quarterly IFRS 17 Close | Quarter-end close scheduler fires | AC002 | 9 | End | Close approved by Finance Controller | AC002 | Quarter signed off
WF002 | Onerous Contract Assessment | New contract group recognised or adverse claims development | AC001 | 1 | Start | Identify contract groups requiring profitability test | AC005 | Groups flagged
WF002 | Onerous Contract Assessment | New contract group recognised or adverse claims development | AC001 | 2 | Action | Calculate fulfilment cashflows for flagged groups per BR004 | AC005 | FCF output
WF002 | Onerous Contract Assessment | New contract group recognised or adverse claims development | AC001 | 3 | Decision | Is group onerous (FCF > premiums)? (BR004) | AC001 | Yes: loss component / No: standard CSM
WF002 | Onerous Contract Assessment | New contract group recognised or adverse claims development | AC001 | 4 | Action | If onerous: recognise loss component immediately in P&L per BR005 | AC005 | Loss component booked
WF002 | Onerous Contract Assessment | New contract group recognised or adverse claims development | AC001 | 5 | End | Assessment documented with actuarial sign-off | AC001 | Audit trail complete

## Business Rules
ID | Name | Category | Priority | Condition | Action | Exception | Source | RelatedReq
BR001 | Best Estimate Liability Calculation | Calculation | Critical | Quarter-end valuation triggered | Calculate BEL as probability-weighted present value of all future cashflows using current discount rates | If data incomplete: use prior quarter BEL with documented adjustment and flag for next quarter | IFRS 17.33 | REQ-001
BR002 | CSM Amortisation Pattern | Calculation | Critical | Coverage period service recognised | Amortise CSM based on coverage units reflecting quantity of service provided in each period | If coverage units cannot be determined: use passage of time as proxy and document rationale | IFRS 17.44 | REQ-002
BR003 | Assumption Update Protocol | Workflow | High | Quarterly or upon significant event | Update actuarial assumptions (mortality/morbidity/lapse/expense) using latest experience data | If credible experience data unavailable: use industry benchmarks with documented margin | IFRS 17.36 | REQ-003
BR004 | Onerous Contract Test | Compliance | Critical | Initial recognition or adverse development | Compare fulfilment cashflows with premium. If FCF > premiums the group is onerous | No exception - all groups must be tested. Document methodology for auditor | IFRS 17.47 | REQ-004
BR005 | Loss Component Recognition | Compliance | Critical | Contract group determined to be onerous per BR004 | Recognise loss immediately in P&L. Allocate subsequent changes between loss component and liability | If group becomes profitable again: reverse loss component through P&L (not through CSM) | IFRS 17.48-52 | REQ-004
BR006 | Discount Rate Selection | Calculation | High | Cashflow projection required | Use bottom-up or top-down approach. Rate must reflect characteristics of cashflows including currency and liquidity | Bottom-up and top-down must produce equivalent results. Document approach and justify selection | IFRS 17.36 | REQ-005
BR007 | Contract Boundary Determination | Validation | High | New policy issued or renewed | Contract boundary ends when insurer can reprice or terminate. Premiums beyond boundary excluded from measurement | For group policies: assess at individual policyholder level unless impractical | IFRS 17.34 | REQ-006
BR008 | Risk Adjustment Calculation | Calculation | Critical | Quarter-end valuation | Calculate RA for non-financial risk using confidence level approach. Target 75th-85th percentile | If confidence level approach not suitable: use cost-of-capital method at 6% rate | IFRS 17.37 | REQ-001

## Contract Fields
Insurance Contract Group: 19 fields ¦ 15 ok ¦ 2 TBI ¦ 2 Gap
Field_Name | Label | Source_Path | Target_Field | Data_Type | Edit_Mode | Mandatory | BR_Ref | Sample_Value | Migration_Status | Compliance_Note
contract_group_id | Contract Group ID | policy.group_id | group_id | String | System | Y |  | GRP-MOTOR-2026-Q1 | ok | IFRS 17 unit of account
measurement_model | Measurement Model | policy.model | model | String | System | Y |  | GMM | ok | GMM/VFA/PAA
cohort_year | Annual Cohort | policy.inception_year | cohort | Integer | System | Y |  | 2026 | ok | IFRS 17 annual cohort requirement
bel_current | Best Estimate Liability | actuarial.bel_current | bel | Decimal | Calculated | Y | BR001 | 4250000.00 | ok
risk_adjustment | Risk Adjustment | actuarial.risk_adjustment | ra | Decimal | Calculated | Y | BR008 | 318750.00 | ok | Typically 5-8% of BEL
csm_opening | CSM Opening Balance | actuarial.csm_opening | csm_open | Decimal | Calculated | Y | BR002 | 890000.00 | ok
csm_amortisation | CSM Amortisation | actuarial.csm_amort | csm_amort | Decimal | Calculated | Y | BR002 | -112500.00 | ok | Negative = P&L release
coverage_units_total | Total Coverage Units | actuarial.cu_total | cu_total | Decimal | Calculated | Y | BR002 | 48000 | ok
coverage_units_current | Current Period Units | actuarial.cu_current | cu_current | Decimal | Calculated | Y | BR002 | 4000 | ok
discount_rate | Discount Rate Applied | actuarial.discount_rate | disc_rate | Decimal | System | Y | BR006 | 0.0285 | ok | 2.85% locked-in rate
onerous_flag | Onerous Indicator | actuarial.onerous | is_onerous | Boolean | Calculated | Y | BR004 | false | ok
loss_component | Loss Component | actuarial.loss_component | loss_comp | Decimal | Calculated | N | BR005 | 0 | ok | Only if onerous
premium_received | Premiums Received | finance.premium_ytd | premium | Decimal | Read | Y |  | 1250000.00 | ok
claims_incurred | Claims Incurred | claims.incurred_ytd | claims | Decimal | Read | Y |  | 780000.00 | ok
experience_adjustment | Experience Adjustment | actuarial.experience_adj | exp_adj | Decimal | Calculated | N |  | 25000.00 | ok | Actual vs expected variance
assumption_change_impact | Assumption Change Impact | actuarial.assumption_impact | assum_impact | Decimal | Calculated | N | BR003 |  | TBI | Impact quantification method not finalised
reinsurance_offset | Reinsurance Offset | reinsurance.offset | ri_offset | Decimal | Read | N |  |  | TBI | Reinsurance held asset mapping pending
solvency_ii_scr | Solvency II SCR | regulatory.scr | scr | Decimal | Read | N |  |  | Gap | Parallel run interface not built yet
embedded_value_bridge | EV to IFRS 17 Bridge | legacy.ev_bridge | ev_bridge | Decimal | Calculated | N |  |  | Gap | No automated reconciliation path

## Traceability
Req_ID | Requirement | User_Story | Test_Case | Test_Steps | Priority | Status
REQ-001 | System shall calculate Best Estimate Liability as probability-weighted PV of future cashflows with risk adjustment at each reporting date | As an actuary I want automated BEL calculation so that quarterly valuations are consistent and auditable | TC-001 | Given motor portfolio Q1 data When actuarial engine runs Then BEL equals sum of discounted cashflows within 0.01% of manual calculation | Critical | Approved
REQ-002 | System shall amortise CSM based on coverage units reflecting quantity of service in each period | As a finance controller I want systematic CSM release so that profit recognition matches service delivery per IFRS 17 | TC-002 | Given group with 48000 total CU and 4000 current CU When amortisation calculated Then CSM release = opening CSM * (4000/48000) per BR002 | Critical | In Progress
REQ-003 | System shall update actuarial assumptions quarterly using latest experience data with documented rationale | As a chief actuary I want assumption governance so that our models reflect current best estimates per IFRS 17.36 | TC-003 | Given mortality experience 5% better than assumed When assumption updated Then BEL decreases and change flows through CSM (not P&L) for non-onerous groups | High | Draft
REQ-004 | System shall test all contract groups for onerousness and recognise loss components immediately in P&L | As an auditor I want transparent onerous testing so that losses are not deferred inappropriately per IFRS 17.47 | TC-004 | Given group where FCF exceeds premiums by 100K When onerous test runs Then loss component of 100K recognised in P&L immediately per BR005 | Critical | Approved
REQ-005 | System shall apply discount rates using bottom-up or top-down approach with documented methodology | As a finance controller I want consistent discount rate application so that liability valuations are comparable | TC-005 | Given EUR portfolio When discount rate selected Then rate reflects risk-free yield curve + illiquidity premium per BR006 | High | Draft
REQ-006 | System shall determine contract boundaries and exclude premiums beyond the boundary from measurement | As an actuary I want correct boundary assessment so that we do not overstate future premium revenue per IFRS 17.34 | TC-006 | Given annual renewable policy When boundary assessed Then measurement includes only current period premiums per BR007 | High | Draft

## Cross-References
Cross-Reference Map
Shows all links between actors, workflows, rules, fields, requirements, and endpoints
Source Type | Source ID | Link Type | Target Type | Target ID | Context
Workflow | WF001 | uses actor | Actor | AC001 | Chief Actuary reviews assumptions (step 4)
Workflow | WF001 | uses actor | Actor | AC002 | Finance Controller approves close (step 9)
Workflow | WF001 | uses actor | Actor | AC005 | Actuarial Engine runs BEL + CSM (steps 3,5,6)
Workflow | WF001 | uses actor | Actor | AC006 | GL receives journal entries (step 7)
Workflow | WF001 | triggers rule | Rule | BR001 | BEL calculation at step 3
Workflow | WF001 | triggers rule | Rule | BR002 | CSM amortisation at step 5
Workflow | WF002 | triggers rule | Rule | BR004 | Onerous contract test
Workflow | WF002 | triggers rule | Rule | BR005 | Loss component recognition
Rule | BR001 | implements | Requirement | REQ-001 | BEL probability-weighted PV of cashflows
Rule | BR001 | controls field | Field | bel_current | Best Estimate Liability output
Rule | BR001 | controls field | Field | risk_adjustment | Risk Adjustment at 75th-85th pctile
Rule | BR002 | implements | Requirement | REQ-002 | CSM release by coverage units
Rule | BR002 | controls field | Field | csm_opening | CSM balance
Rule | BR002 | controls field | Field | csm_amortisation | Period release amount
Rule | BR002 | controls field | Field | coverage_units_total | Denominator
Rule | BR002 | controls field | Field | coverage_units_current | Numerator
Rule | BR004 | implements | Requirement | REQ-004 | Onerous test: FCF vs premiums
Rule | BR004 | controls field | Field | onerous_flag | Boolean indicator
Rule | BR005 | controls field | Field | loss_component | P&L loss for onerous groups
Rule | BR006 | implements | Requirement | REQ-005 | Discount rate bottom-up or top-down
Rule | BR006 | controls field | Field | discount_rate | Locked-in or current rate
Field | assumption_change_impact | status: TBI | Source | N/A | Quantification method not finalised
Field | reinsurance_offset | status: TBI | Source | N/A | Reinsurance held asset mapping pending
Field | solvency_ii_scr | status: Gap | Source | N/A | Parallel run interface not built
Field | embedded_value_bridge | status: Gap | Source | N/A | No automated EV-to-IFRS17 reconciliation

## RACI Matrix
RACI Matrix
R = Responsible (does the work) ¦ A = Accountable (owns the outcome) ¦ C = Consulted (provides input) ¦ I = Informed (kept updated)
Deliverable / Activity | Chief Actuary | Finance Controller | Claims Handler | Actuarial Engine | GL / Subledger | Solvency II Engine | Close Scheduler
IFRS 17 measurement models | A |  |  | R
CSM amortisation engine | A | C |  | R
Assumption governance | R | A
Onerous contract testing | R | A |  | R
GL journal generation |  | A |  | R | R
Disclosure pack | C | R
Solvency II parallel run | C | A |  |  |  | R
UAT execution | R | R | R
Quarter-end close process | C | A |  |  |  |  | R

## Risk Register
Risk Register
Risk ID | Description | Category | Probability (1-5) | Impact (1-5) | Score | Mitigation | Owner | Status | Linked REQ
RSK-001 | Actuarial assumption changes between quarters cause material CSM movements that auditors challenge | Financial | 4 | 4 |  | Document assumption change protocol. Pre-agree materiality thresholds with auditor. Quarterly review board. | Chief Actuary | Mitigating | REQ-003
RSK-002 | Solvency II parallel run interface delays block IFRS 17 go-live | Integration | 3 | 4 |  | Decouple timelines. IFRS 17 can go live without SII parallel run. Manual reconciliation as interim. | Finance Controller | Open
RSK-003 | Coverage unit methodology not accepted by auditor for CSM amortisation pattern | Regulatory | 3 | 5 |  | Pre-clear methodology with auditor. Prepare passage-of-time fallback. Document both approaches. | Chief Actuary | Open | REQ-002
RSK-004 | Embedded Value to IFRS 17 bridge reconciliation cannot be automated | Technical | 4 | 3 |  | Accept manual reconciliation for first 2 quarters. Build automated bridge in phase 2. | Finance Controller | Accepted

## NFRs
Non-Functional Requirements
NFR ID | Category | Requirement | Metric | Target | Measurement Method | Priority | Linked Entity
NFR-001 | Performance | Quarterly actuarial run for full portfolio must complete within 4-hour batch window | Batch duration | < 4 hours | Timed test run on full production data. Parallel processing benchmark. | Critical | Contract Group
NFR-002 | Availability | Actuarial engine must be available for ad-hoc reruns within 2 hours of request during close period | Recovery time | < 2h restart | Warm standby. Pre-configured rerun scripts. | High
NFR-003 | Compliance | All CSM movements must be traceable to specific assumption or experience changes for audit | Traceability completeness | 100% of CSM deltas explained | Waterfall decomposition report. Audit sample testing. | Critical | Contract Group

## Assumptions
Assumptions & Dependencies
ID | Type | Description | Impact if Wrong | Validated | Owner | Date | Linked Risk
A-001 | Assumption | Auditor will accept coverage unit approach (not passage-of-time) for CSM amortisation | If rejected: entire CSM engine logic must be reworked. 8-12 week delay. | Pending | Chief Actuary | 2026-02-01 | RSK-003
A-002 | Dependency | Prophet actuarial model outputs must be available in IFRS 17-compatible format by Q2 2026 | If format changes: ETL pipeline rebuild. 4-6 weeks delay. | Pending | Actuarial IT | 2026-01-15
A-003 | Constraint | Existing GL chart of accounts cannot be modified — IFRS 17 journals must map to current structure | May require sub-account layer. Adds complexity to journal generation. | Yes | Finance Controller | 2025-12-20

## Decision Log
Decision Log
ID | Decision | Rationale | Alternatives Considered | Decided By | Date | Status | Linked REQ/BR
DEC-001 | Use General Measurement Model (GMM) for all long-duration contracts, PAA for short-tail only | GMM provides full CSM tracking. PAA simplification only appropriate for <12 month coverage. | 1. PAA for all (non-compliant for long-tail). 2. VFA for participating (not applicable to non-life). | Chief Actuary + Auditor | 2025-11-15 | Approved | BR001, BR002
DEC-002 | Use bottom-up approach for discount rate construction | More transparent than top-down. Risk-free yield curve + illiquidity premium. Auditor preference. | 1. Top-down (deduct credit spread from asset yield). 2. OCI option (reduces P&L volatility but adds complexity). | Chief Actuary | 2025-12-01 | Approved | BR006, REQ-005

## Data Volumes
Data Volume & Sizing Estimates
Entity | Current Rows | Annual Growth % | Projected at Go-Live | Peak Concurrent Users | API Calls/Min (Peak) | Avg Record Size (KB) | Total Storage (GB) | SLA Target
Insurance Contract Groups | 450 | 8 |  | 15 | 0 | 25 |  | < 4h batch processing
Individual Policies | 2500000 | 5 |  | 200 | 0 | 3.5 |  | Real-time policy admin
Claims Records | 180000 | 7 |  | 50 | 0 | 8 |  | < 1s retrieval
Actuarial Cashflow Projections | 54000000 | 10 |  | 5 | 0 | 0.2 |  | Batch only
GL Journal Entries | 50000 | 12 |  | 10 | 0 | 0.8 |  | < 30min posting
TOTAL

## Change Requests
Change Request Register
CR ID | Title | Description | Requestor | Date | Impact | Effort (days) | Affected REQs | Affected Fields | Status | Approved By
CR-001 | Add reinsurance offset calculation to quarterly close | Reinsurance held asset must be calculated alongside BEL for net position reporting. | Chief Actuary | 2026-03-15 | High | 10 | REQ-001 | reinsurance_offset | Approved | Finance Controller
CR-002 | Add PAA eligibility test for short-tail contracts | Need automated test to determine if PAA simplification can be applied vs full GMM. | Actuarial Team | 2026-03-20 | Medium | 5 | REQ-002 | measurement_model | Assessing

## Open Questions
ID | Question | Context | Entity_Field | Priority | Status | Assigned_To | Answer
Q001 | Will the auditor accept coverage unit approach for CSM amortisation? | Alternative is passage-of-time which is simpler but less accurate | coverage_units_total | Critical | Open | Chief Actuary
Q002 | What discount rate methodology will be used — bottom-up or top-down? | Both should produce equivalent results per IFRS 17.36 | discount_rate | High | Answered | Chief Actuary | Bottom-up approach approved (DEC-002)
Q003 | How should the EV-to-IFRS 17 bridge reconciliation be performed? | No automated path exists. Manual reconciliation may be needed for first quarters. | embedded_value_bridge | High | Open | Finance Controller
Q004 | What is the materiality threshold for assumption changes triggering CSM recalculation? | Need to avoid trivial recalculations that consume actuarial engine capacity | assumption_change_impact | Medium | Open | Chief Actuary

## Glossary
Term | Definition | Related_Entity
BEL | Best Estimate Liability. Probability-weighted present value of all future cashflows. | Contract Group
CSM | Contractual Service Margin. Unearned profit recognised over coverage period. | Contract Group
GMM | General Measurement Model. Full IFRS 17 measurement approach for long-duration contracts. | Contract Group
PAA | Premium Allocation Approach. Simplified IFRS 17 measurement for short-duration contracts. | Contract Group
VFA | Variable Fee Approach. IFRS 17 model for contracts with direct participation features.
FCF | Fulfilment Cash Flows. Expected cash flows including risk adjustment and time value of money. | Contract Group
RA | Risk Adjustment. Compensation for bearing non-financial risk uncertainty. | Contract Group
SCR | Solvency Capital Requirement. Minimum capital under Solvency II regulatory framework.
ORSA | Own Risk and Solvency Assessment. Internal risk assessment required by Solvency II.
Prophet | Actuarial modelling platform used for IFRS 17 cashflow projections. | Contract Group