## Overview
BAForge Workshop Input Templates
One structured capture template per methodology task. Print, fill in workshops, then enter data into BAForge.
TEMPLATE INDEX
Task | Title | Phase | Step | Category | Tool | Duration | Workshop Type
T01 | Define Project Scope | Plan | Setup | Scoping | BAForge Agent > Setup | 2 hours | Kickoff meeting
T02 | Assess Current State | Plan | Discovery | Analysis | BAForge Agent > Discovery | 3-5 days | Stakeholder interviews (1h each)
T03 | Design Target State | Plan | Design | Specification | BAForge Agent > Design | Half day | Design workshop (half-day)
T04 | Run Compliance Assessment | Plan | Discovery | Quality | BAForge Agent > Discovery (Compliance) | 2-3 hours | Compliance review with legal/regulatory team
T05 | Define Actors & Permissions | Define | Business Logic | Specification | BAForge Agent > Business Logic > Actors | 2 hours | Actor mapping session
T06 | Define Business Rules | Define | Business Logic | Specification | BAForge Agent > Business Logic > Rules | Half day | Rules elicitation with domain experts
T07 | Map Workflows | Define | Business Logic | Specification | BAForge Agent > Business Logic > Workflows | Half day per workflow | Process mapping with end users
T08 | Build Data Model | Define | Data Model | Data Modelling | BAForge Agent > Data Model | 1-2 days per entity | Data mapping with architects + source system owners
T10 | Specify API Endpoints | Define | API Specs | Integration | BAForge Agent > API Specs | Half day | API review with integration team
T11 | Define Technical Specifications | Execute | Build | Specification | BAForge Agent > Build | Half day | Technical design review
T12 | Plan Transition & Handover | Execute | Deploy | Delivery | BAForge Agent > Deploy | Half day | Transition planning with PMO + change management
T15 | Build Traceability Matrix | Validate | Traceability | Quality | BAForge Agent > Traceability | 2-3 hours | Traceability review with QA lead and BA
T27 | Maintain Risk Register | Govern | Governance | Governance | BAForge Agent > Governance > Risks | 1-2 hours per review | Risk review at each phase gate
T30 | Define Non-Functional Requirements | Govern | NFRs & Sizing | Governance | BAForge Agent > NFRs & Sizing > NFRs | Half day | NFR elicitation with architects + security + operations
T31 | Estimate Data Volumes | Govern | NFRs & Sizing | Governance | BAForge Agent > NFRs & Sizing > Data Volumes | 2-3 hours | Sizing session with DBAs + architects
EXPORT SHEETS — BAForge Import Guide
Export Sheet | Source Workshop | BAForge Layout | Import Target | Method | Rows
Export Actors | T05 Actors | actors | Agent > Business Logic > Actors > Import CSV |  |  | Formula
Export Rules | T06 Rules | rules | Agent > Business Logic > Rules > Import CSV |  |  | Formula
Export Workflows | T07 Workflows | workflows | Agent > Business Logic > Workflows > Import CSV |  |  | Formula
Export Fields | T08 DataModel | fields | Agent > Data Model > (entity) > Import CSV: Fields |  |  | Formula
Export Endpoints | T09 APIs | apiEndpoints | Agent > API Specs > Import CSV |  |  | Formula
Export Requirements | T03 To-Be | traceability | Agent > Traceability > Import CSV |  |  | Formula
Export Questions | Multiple | openQuestions | Agent > Open Items > Questions > Import CSV |  |  | Manual
Export Glossary | Multiple | glossary | Agent > Open Items > Glossary > Import CSV |  |  | Manual
Export Risks | T13 Risks | risks | Agent > Governance > Risks (manual entry) |  |  | Formula
Export NFRs | T14 NFRs | nfrs | Agent > NFRs & Sizing > NFRs (manual entry) |  |  | Formula
Export Volumes | T15 Volumes | dataVolumes | Agent > NFRs & Sizing > Data Volumes (manual entry) |  |  | Formula

## T01 Scope
T01 Define Project Scope
Stage: Plan ¦ Step: Setup ¦ Category: Scoping ¦ Tool: BAForge Agent > Setup
Goal: Establish project identity, boundaries, methodology, and key parameters
WORKSHOP LOGISTICS
Date |  |  |  | Duration | 2 hours
Facilitator |  |  |  | Location / Link
Workshop Type | Kickoff meeting |  |  | Project
ATTENDEES
# | Name | Role | Organisation | Email | Present (Y/N) | Action Owner | Notes
1
2
3
4
5
6
PREPARATION CHECKLIST
# | Input Required | Source | Status | Owner | Notes
1 | Project brief or RFP |  | Sponsor
2 | Organisational chart |  | HR / PMO
3 | Budget approval document |  | Finance
4 | Strategic roadmap |  | CTO office
WORKSHOP CAPTURE
Project identity
Project Name | e.g. IMMOGEST Financial Hub Integration
Client / Organisation | e.g. EEAS — European External Action Service
Sponsor Name & Role
Project Manager
Project parameters
Industry / Domain | EU Institutions / Banking / Insurance / Telecom / Energy / Public Sector / Healthcare
Transformation Type | System Migration / Digital Transformation / Process Reengineering / Regulatory / BI / ERP / Cloud
Methodology | Agile / Waterfall / Hybrid / SAFe / Lean Six Sigma / PRINCE2
Timeline | e.g. Q3 2026 — Q1 2027
Budget Range | e.g. 500K — 1M EUR
Scope boundaries
In Scope | What is included in this project...
Out of Scope | What is explicitly excluded...
Key Constraints | Hard deadlines, fixed tech, regulatory mandates...
Dependencies on Other Projects | Projects that must deliver before or alongside this one...
EXPECTED OUTPUTS
# | Output | Status | Owner | Uploaded to BAForge | Notes
1 | Project name and client
2 | Domain and transformation type
3 | Timeline and budget range
4 | Methodology selection
5 | Key constraints
ACTIONS & FOLLOW-UPS
# | Action | Owner | Due Date | Priority | Status | Linked Task | Notes
CONNECTED TASKS (cross-reference)
T02 | Scope defines what to discover
T03 | Scope constrains the design
T26 | Project metadata feeds the RACI matrix
SFL Consulting ¦ BAForge v3.1 ¦ Workshop Template

## T02 As-Is
T02 Assess Current State
Stage: Plan ¦ Step: Discovery ¦ Category: Analysis ¦ Tool: BAForge Agent > Discovery
Goal: Document As-Is systems, processes, pain points, and stakeholder landscape
WORKSHOP LOGISTICS
Date |  |  |  | Duration | 3-5 days
Facilitator |  |  |  | Location / Link
Workshop Type | Stakeholder interviews (1h each) |  |  | Project
ATTENDEES
# | Name | Role | Organisation | Email | Present (Y/N) | Action Owner | Notes
1
2
3
4
5
6
PREPARATION CHECKLIST
# | Input Required | Source | Status | Owner | Notes
1 | Existing system documentation |  | IT / System owners
2 | Process maps |  | Process owners
3 | Organisation chart |  | HR
4 | User feedback / support tickets |  | Service desk
WORKSHOP CAPTURE
Stakeholder register
# | Name | Role | Department | Influence (H/M/L) | Interest (H/M/L) | Engagement Strategy | Notes
1 | Maria Gonzalez | Head of Real Estate | HQ Admin | High | High | Bi-weekly steering | Project sponsor
Current systems inventory
# | System Name | Vendor / Type | Purpose | Users | Data Volumes | Integration Points | Pain Points
1 | IMMOGEST | Java / Oracle | Real estate management | 500+ | ~5K contracts | ABAC, ARES, EU Login | ABAC decommission
Pain points (prioritised)
# | Pain Point | Impact Area | Severity (1-5) | Frequency | Affected Users | Current Workaround | Root Cause
As-Is narrative
Current state description | Describe the current systems, processes, and how they work together...
Data landscape | Data sources, volumes, quality issues, integration patterns...
Regulatory context | Which regulations apply, current compliance status...
EXPECTED OUTPUTS
# | Output | Status | Owner | Uploaded to BAForge | Notes
1 | Stakeholder register with roles and influence
2 | As-Is situation narrative
3 | Pain points list (prioritised)
4 | Existing systems inventory
5 | Data landscape overview
6 | Initial risk list
ACTIONS & FOLLOW-UPS
# | Action | Owner | Due Date | Priority | Status | Linked Task | Notes
CONNECTED TASKS (cross-reference)
T01 | Discovery is bounded by scope
T03 | As-Is feeds gap analysis in design
T04 | Stakeholders become actors
T27 | Identified risks feed risk register
T28 | Assumptions surface during discovery
SFL Consulting ¦ BAForge v3.1 ¦ Workshop Template

## T03 To-Be
T03 Design Target State
Stage: Plan ¦ Step: Design ¦ Category: Specification ¦ Tool: BAForge Agent > Design
Goal: Define To-Be architecture, requirements, KPIs, and constraints
WORKSHOP LOGISTICS
Date |  |  |  | Duration | Half day
Facilitator |  |  |  | Location / Link
Workshop Type | Design workshop (half-day) |  |  | Project
ATTENDEES
# | Name | Role | Organisation | Email | Present (Y/N) | Action Owner | Notes
1
2
3
4
5
6
PREPARATION CHECKLIST
# | Input Required | Source | Status | Owner | Notes
1 | As-Is documentation (T02) |  | BA Lead (T02)
2 | Business strategy |  | Strategy team
3 | Regulatory requirements |  | Legal / Compliance
4 | Technology roadmap |  | CTO / Architecture
WORKSHOP CAPTURE
To-Be vision
Target state description | Describe the desired end state — architecture, processes, user experience...
Key changes from As-Is | What specifically changes between current and target state...
High-level requirements
REQ ID | Requirement | Priority | Acceptance Criteria | Regulatory Ref | Source | MoSCoW | Notes
REQ-001 | System shall enforce valid contract status transitions | Critical | Only DRAFT>IN_FORCE>EXPIRED>ARCHIVED allowed | EU Financial Reg | Design workshop | Must
KPIs and success criteria
# | KPI | Current Baseline | Target Value | Measurement Method | Measurement Frequency | Owner
User stories
US ID | As a [role] | I want [capability] | So that [benefit] | Linked REQ | Priority | Acceptance Criteria
EXPECTED OUTPUTS
# | Output | Status | Owner | Uploaded to BAForge | Notes
1 | To-Be vision document
2 | High-level requirements (REQ-XXX)
3 | Success KPIs
4 | Integration requirements
5 | Key user stories
6 | Design constraints
ACTIONS & FOLLOW-UPS
# | Action | Owner | Due Date | Priority | Status | Linked Task | Notes
CONNECTED TASKS (cross-reference)
T02 | Design addresses As-Is pain points
T06 | Requirements drive business rules
T08 | Requirements feed field-level specs
T15 | Requirements traced to test cases
T29 | Design decisions are logged
T30 | NFRs complement functional requirements
SFL Consulting ¦ BAForge v3.1 ¦ Workshop Template

## T04 Compliance
T04 Run Compliance Assessment
Stage: Plan ¦ Step: Discovery ¦ Category: Quality ¦ Tool: BAForge Agent > Discovery (Compliance)
Goal: Identify applicable regulations and assess compliance readiness per domain
WORKSHOP LOGISTICS
Date |  |  |  | Duration | 2-3 hours
Facilitator |  |  |  | Location / Link
Workshop Type | Compliance review with legal/regulatory team |  |  | Project
ATTENDEES
# | Name | Role | Organisation | Email | Present (Y/N) | Action Owner | Notes
1
2
3
4
5
6
PREPARATION CHECKLIST
# | Input Required | Source | Status | Owner | Notes
1 | Domain selection (T01) |  | T01 output
2 | Regulatory framework documents |  | Legal team
3 | Existing compliance reports |  | Compliance team
4 | Audit findings |  | Internal audit
WORKSHOP CAPTURE
Regulatory applicability assessment
Regulation | Applicable (Y/N) | Critical | Key Requirements | Current Status | Gap | Remediation | Owner
EU Financial Regulation | Y | Critical | Budget implementation, commitment workflows, audit trail | Partial | SUMMA alignment needed | Map ABAC workflows to SUMMA | Finance Unit
Compliance checks
# | Item | Status | Evidence / Notes
1 | Data Protection Impact Assessment (DPIA) completed
2 | Data Processing Register updated
3 | Consent mechanisms in place
4 | Breach notification procedure defined
5 | Access control matrix documented
6 | Audit trail requirements specified
7 | Incident response plan updated
8 | Business continuity plan reviewed
9 | Security classification applied
10 | Cross-border transfer assessment done
EXPECTED OUTPUTS
# | Output | Status | Owner | Uploaded to BAForge | Notes
1 | Compliance checklist (domain-specific)
2 | Critical vs non-critical regulation map
3 | Compliance readiness %
4 | Compliance gaps for remediation
ACTIONS & FOLLOW-UPS
# | Action | Owner | Due Date | Priority | Status | Linked Task | Notes
CONNECTED TASKS (cross-reference)
T01 | Domain determines which regulations apply
T06 | Compliance checks become business rules
T17 | Compliance readiness gates document generation
T27 | Compliance gaps feed risk register
SFL Consulting ¦ BAForge v3.1 ¦ Workshop Template

## T05 Actors
T05 Define Actors & Permissions
Stage: Define ¦ Step: Business Logic ¦ Category: Specification ¦ Tool: BAForge Agent > Business Logic > Actors
Goal: Catalogue all system actors with types, CRUD permissions, and data access scope
WORKSHOP LOGISTICS
Date |  |  |  | Duration | 2 hours
Facilitator |  |  |  | Location / Link
Workshop Type | Actor mapping session |  |  | Project
ATTENDEES
# | Name | Role | Organisation | Email | Present (Y/N) | Action Owner | Notes
1
2
3
4
5
6
PREPARATION CHECKLIST
# | Input Required | Source | Status | Owner | Notes
1 | Stakeholder register (T02) |  | T02 output
2 | System access matrix |  | IT Security
3 | Role definitions |  | HR / IAM
4 | Security policy |  | Security team
WORKSHOP CAPTURE
Actor catalogue
Actor ID | Name | Type | Description | C | R | U | D
AC001 | HQ User Admin | Primary Actor | Full admin rights across all delegations | Y | Y | Y | Y
AC005 | Financial Hub | System Actor | External financial system providing LCK/LEF/BAF |  | Y
Permission scope
Actor ID | Data Scope | Geographic Scope | Time Restrictions | Delegation Rules | Escalation Path
EXPECTED OUTPUTS
# | Output | Status | Owner | Uploaded to BAForge | Notes
1 | Actor catalogue (AC001-ACnnn)
2 | Actor types
3 | CRUD matrix per actor
4 | Permission scope per actor
ACTIONS & FOLLOW-UPS
# | Action | Owner | Due Date | Priority | Status | Linked Task | Notes
CONNECTED TASKS (cross-reference)
T02 | Stakeholders become actors
T06 | Actors participate in workflows
T07 | Actors own workflow steps
T20 | Actors map to Jira components
T26 | Actors populate RACI columns
SFL Consulting ¦ BAForge v3.1 ¦ Workshop Template

## T06 Rules
T06 Define Business Rules
Stage: Define ¦ Step: Business Logic ¦ Category: Specification ¦ Tool: BAForge Agent > Business Logic > Rules
Goal: Capture all IF/THEN/ELSE business rules with categories, priorities, and regulatory sources
WORKSHOP LOGISTICS
Date |  |  |  | Duration | Half day
Facilitator |  |  |  | Location / Link
Workshop Type | Rules elicitation with domain experts |  |  | Project
ATTENDEES
# | Name | Role | Organisation | Email | Present (Y/N) | Action Owner | Notes
1
2
3
4
5
6
PREPARATION CHECKLIST
# | Input Required | Source | Status | Owner | Notes
1 | Requirements (T03) |  | T03 output
2 | Compliance checklist (T04) |  | T04 output
3 | Existing business rules |  | Business owners
4 | Regulatory texts |  | Legal
WORKSHOP CAPTURE
Business rules catalogue
BR ID | Name | Category | Priority | IF (condition) | THEN (action) | ELSE (exception) | Source
BR053 | LCK Format Validation | Validation | Critical | LCK reference entered | Validate format EAS.XXXXXX | Show error per BR064 | FH Spec
BR055 | BAF Validation | Compliance | Critical | Bank account retrieved | Check IBAN + status + earlyWarning + expiry | Block contract creation | FH Spec
Rule-to-requirement mapping
BR ID | Linked REQ | Linked Workflow Step | Linked Field(s) | Regulatory Reference | Audit Impact
EXPECTED OUTPUTS
# | Output | Status | Owner | Uploaded to BAForge | Notes
1 | Business rules catalogue (BR001-BRnnn)
2 | IF/THEN/ELSE per rule
3 | Category and priority
4 | Source reference and linked REQ
ACTIONS & FOLLOW-UPS
# | Action | Owner | Due Date | Priority | Status | Linked Task | Notes
CONNECTED TASKS (cross-reference)
T03 | Requirements drive rule creation
T04 | Compliance checks become rules
T07 | Rules are triggered within workflows
T08 | Rules reference specific fields (BR_Ref)
T10 | Rules map to API validation
T15 | Rules traced through requirements
T20 | Rules become Jira tasks
SFL Consulting ¦ BAForge v3.1 ¦ Workshop Template

## T07 Workflows
T07 Map Workflows
Stage: Define ¦ Step: Business Logic ¦ Category: Specification ¦ Tool: BAForge Agent > Business Logic > Workflows
Goal: Document step-by-step workflows with actors, triggers, decisions, and outputs
WORKSHOP LOGISTICS
Date |  |  |  | Duration | Half day per workflow
Facilitator |  |  |  | Location / Link
Workshop Type | Process mapping with end users |  |  | Project
ATTENDEES
# | Name | Role | Organisation | Email | Present (Y/N) | Action Owner | Notes
1
2
3
4
5
6
PREPARATION CHECKLIST
# | Input Required | Source | Status | Owner | Notes
1 | Actor catalogue (T05) |  | T05 output
2 | Business rules (T06) |  | T06 output
3 | As-Is process maps (T02) |  | T02 output
WORKSHOP CAPTURE
Workflow header
Workflow ID | WF001
Workflow Name | e.g. Contract Creation
Trigger Event | What starts this workflow?
Owner (Actor) | Which actor owns this process?
Pre-conditions | What must be true before this workflow can start?
Post-conditions | What is true after this workflow completes?
Workflow steps
Step # | Type | Description | Actor | Input | Output | Business Rule | Decision Branch
1 | Start | Navigate to Building > Contracts | AC004 | Building ID | Form displayed
2 | Action | Enter LCK reference (EAS.XXXXXX) | AC004 | LCK value | LCK entered | BR053
3 | Decision | Is LCK format valid? | AC005 | LCK | Valid/Invalid | BR064 | Yes: step 4 / No: error
EXPECTED OUTPUTS
# | Output | Status | Owner | Uploaded to BAForge | Notes
1 | Workflow catalogue (WF001-WFnnn)
2 | Steps with type/description/actor/output
3 | Trigger events
4 | Decision points with branch logic
ACTIONS & FOLLOW-UPS
# | Action | Owner | Due Date | Priority | Status | Linked Task | Notes
CONNECTED TASKS (cross-reference)
T05 | Actors execute steps
T06 | Rules triggered at specific steps
T08 | Workflows reference entity fields
T10 | API calls are subprocesses
T20 | Workflows become Jira Epics
SFL Consulting ¦ BAForge v3.1 ¦ Workshop Template

## T08 DataModel
T08 Build Data Model
Stage: Define ¦ Step: Data Model ¦ Category: Data Modelling ¦ Tool: BAForge Agent > Data Model
Goal: Define entities with field-level source-to-target mapping and migration status
WORKSHOP LOGISTICS
Date |  |  |  | Duration | 1-2 days per entity
Facilitator |  |  |  | Location / Link
Workshop Type | Data mapping with architects + source system owners |  |  | Project
ATTENDEES
# | Name | Role | Organisation | Email | Present (Y/N) | Action Owner | Notes
1
2
3
4
5
6
PREPARATION CHECKLIST
# | Input Required | Source | Status | Owner | Notes
1 | Source system schemas / data dictionaries |  | Source DBA
2 | Target system specs / API docs |  | Target system team
3 | Business rules (T06) |  | T06 output
4 | API response samples |  | Integration team
WORKSHOP CAPTURE
Entity definition
Entity ID | ENT01
Entity Name | e.g. Legal Commitment (LCK)
Source System | e.g. Financial Hub / SUMMA
Description | What this entity represents...
Field mapping
Field Name | Label | Source Path | Target Field | Type | Edit Mode | Mandatory | Migration Status
local_key | LCK Ref | local_key | lck_reference | String | Read | Y | ok
notice_period | Notice Period | N/A | notice_period | Integer | Edit | N | TBI
Field details (per field requiring explanation)
Field Name | BR Reference | Sample Value | Compliance Note | Transformation Rule | Validation | WF Usage | Notes
EXPECTED OUTPUTS
# | Output | Status | Owner | Uploaded to BAForge | Notes
1 | Entity catalogue (ENT01-ENTnn)
2 | Field mapping per entity
3 | TBI/Gap field identification
4 | Workflow-field usage matrix
ACTIONS & FOLLOW-UPS
# | Action | Owner | Due Date | Priority | Status | Linked Task | Notes
CONNECTED TASKS (cross-reference)
T06 | Fields reference rules via BR_Ref
T07 | Fields used in workflow steps
T10 | Fields map to API payloads
T13 | TBI fields become questions
T15 | Field requirements are traced
T31 | Entities drive volume estimates
SFL Consulting ¦ BAForge v3.1 ¦ Workshop Template

## T09 APIs
T10 Specify API Endpoints
Stage: Define ¦ Step: API Specs ¦ Category: Integration ¦ Tool: BAForge Agent > API Specs
Goal: Document each API endpoint with method, path, entity, auth, call sequence, and error codes
WORKSHOP LOGISTICS
Date |  |  |  | Duration | Half day
Facilitator |  |  |  | Location / Link
Workshop Type | API review with integration team |  |  | Project
ATTENDEES
# | Name | Role | Organisation | Email | Present (Y/N) | Action Owner | Notes
1
2
3
4
5
6
PREPARATION CHECKLIST
# | Input Required | Source | Status | Owner | Notes
1 | API documentation / Swagger |  | Source system API docs
2 | Data model (T08) |  | T08 output
3 | Business rules (T06) |  | T06 output
4 | Security requirements |  | Security team
WORKSHOP CAPTURE
Endpoint specification
Endpoint ID | EP01
Method | GET / POST / PUT / PATCH / DELETE
Path | /legal-commitments/{localKey}/last-validated
Description | Retrieve legal commitment data by local key
Entity | LCK
Authentication | OAuth 2.0 / API Key / mTLS
Rate Limiting | 100 req/min per client
Call sequence
Call sequence | 1. Call with key 2. Extract sub-keys from response 3. Trigger parallel calls to EP02 + EP03
Error codes
HTTP Code | Error Name | Description | Retry Strategy | Fallback Action | Linked BR
200 | Success | Data returned successfully | N/A | N/A
404 | Not Found | Entity not found with given key | No retry | Show user-friendly error per BR064 | BR064
EXPECTED OUTPUTS
# | Output | Status | Owner | Uploaded to BAForge | Notes
1 | Endpoint catalogue (EP01-EPnn)
2 | Method/path/description
3 | Request/response samples
4 | Error code catalogue
5 | Call sequence and rate limiting
ACTIONS & FOLLOW-UPS
# | Action | Owner | Due Date | Priority | Status | Linked Task | Notes
CONNECTED TASKS (cross-reference)
T06 | Endpoints enforce rules
T07 | API calls are workflow subprocesses
T08 | Endpoints return entity field data
T15 | API behaviour is requirement-traced
T20 | Integration work maps to Jira
SFL Consulting ¦ BAForge v3.1 ¦ Workshop Template

## T10 TechSpecs
T11 Define Technical Specifications
Stage: Execute ¦ Step: Build ¦ Category: Specification ¦ Tool: BAForge Agent > Build
Goal: Document tech stack, migration approach, testing strategy, audit controls, security, and reporting
WORKSHOP LOGISTICS
Date |  |  |  | Duration | Half day
Facilitator |  |  |  | Location / Link
Workshop Type | Technical design review |  |  | Project
ATTENDEES
# | Name | Role | Organisation | Email | Present (Y/N) | Action Owner | Notes
1
2
3
4
5
6
PREPARATION CHECKLIST
# | Input Required | Source | Status | Owner | Notes
1 | Data model (T08) |  | T08 output
2 | API specs (T10) |  | T10 output
3 | NFRs (T30) |  | T30 output
4 | Compliance assessment (T04) |  | T04 output
WORKSHOP CAPTURE
Technology stack
Layer | Technology | Version | Purpose | License | Support Status | Alternative Considered | Decision Ref
Frontend | Java / Oracle | 11 / 19c | Application server + DB | Oracle License | Active | PostgreSQL (rejected: Oracle mandated) | DEC-001
Testing strategy
Test levels | Unit > Integration > System > UAT > Performance > Security
Test environments | DEV > SIT > UAT > PRE-PROD > PROD
UAT acceptance criteria | All critical test cases pass, zero P1 defects, <5 P2...
Test data strategy | Anonymised production data / synthetic data / test data generators...
Audit & security
Audit trail requirements | What changes must be logged, retention period, ISAE 3402...
Authentication | EU Login SSO / OAuth 2.0 / SAML / mTLS...
Encryption | At rest (AES-256), in transit (TLS 1.3), key management...
EXPECTED OUTPUTS
# | Output | Status | Owner | Uploaded to BAForge | Notes
1 | Technology stack decision
2 | Data migration rules
3 | Testing strategy and UAT criteria
4 | Audit trail requirements
5 | Security requirements
6 | Reporting specs
ACTIONS & FOLLOW-UPS
# | Action | Owner | Due Date | Priority | Status | Linked Task | Notes
CONNECTED TASKS (cross-reference)
T08 | Tech specs implement data model
T10 | Tech specs cover API infrastructure
T12 | Tech feeds deployment planning
T30 | NFRs constrain technical decisions
T04 | Compliance drives audit controls
T29 | Technical choices are logged as decisions
SFL Consulting ¦ BAForge v3.1 ¦ Workshop Template

## T11 Deploy
T12 Plan Transition & Handover
Stage: Execute ¦ Step: Deploy ¦ Category: Delivery ¦ Tool: BAForge Agent > Deploy
Goal: Define rollout strategy, training plan, handover deliverables, hypercare, and go-live criteria
WORKSHOP LOGISTICS
Date |  |  |  | Duration | Half day
Facilitator |  |  |  | Location / Link
Workshop Type | Transition planning with PMO + change management |  |  | Project
ATTENDEES
# | Name | Role | Organisation | Email | Present (Y/N) | Action Owner | Notes
1
2
3
4
5
6
PREPARATION CHECKLIST
# | Input Required | Source | Status | Owner | Notes
1 | Technical specs (T11) |  | T11 output
2 | Actor catalogue (T05) |  | T05 output
3 | Risk register (T27) |  | T27 output
4 | Data volumes (T31) |  | T31 output
WORKSHOP CAPTURE
Rollout strategy
Approach | Phased by region / Big-bang / Parallel run / Pilot + rollout
Phases / Waves | Wave 1: 28 delegations (Western Europe), Wave 2: ...
Rollback criteria | If X then rollback: steps to revert to previous state...
Data freeze window | When does data entry stop before cutover? How long?
Go-live checklist
# | Item | Status | Evidence / Notes
1 | All critical UAT test cases passed
2 | Zero P1 defects open
3 | Data migration verified (100% match)
4 | Rollback procedure tested
5 | Training completed for all actor roles
6 | Hypercare team on standby
7 | Communication sent to all users
8 | Monitoring and alerting configured
9 | Sign-off from project sponsor
10 | Sign-off from IT security
Training plan
Actor Role | Training Type | Duration | Format | Trainer | Materials | Assessment | Schedule
EXPECTED OUTPUTS
# | Output | Status | Owner | Uploaded to BAForge | Notes
1 | Rollout strategy
2 | Training plan per actor role
3 | Handover deliverables
4 | Hypercare plan and SLAs
5 | Go-live decision criteria
ACTIONS & FOLLOW-UPS
# | Action | Owner | Due Date | Priority | Status | Linked Task | Notes
CONNECTED TASKS (cross-reference)
T11 | Deployment builds on tech specs
T05 | Training targets actor roles
T27 | Risk mitigations feed rollout strategy
T31 | Data volumes drive infrastructure sizing
SFL Consulting ¦ BAForge v3.1 ¦ Workshop Template

## T12 Trace
T15 Build Traceability Matrix
Stage: Validate ¦ Step: Traceability ¦ Category: Quality ¦ Tool: BAForge Agent > Traceability
Goal: Map every requirement to user story, test case, and test steps — end-to-end trace
WORKSHOP LOGISTICS
Date |  |  |  | Duration | 2-3 hours
Facilitator |  |  |  | Location / Link
Workshop Type | Traceability review with QA lead and BA |  |  | Project
ATTENDEES
# | Name | Role | Organisation | Email | Present (Y/N) | Action Owner | Notes
1
2
3
4
5
6
PREPARATION CHECKLIST
# | Input Required | Source | Status | Owner | Notes
1 | Requirements (T03) |  | T03 output
2 | Business rules (T06) |  | T06 output
3 | User stories (T03) |  | T03 output
WORKSHOP CAPTURE
Traceability matrix
REQ ID | Requirement | User Story | Test Case ID | Test Steps (Given/When/Then) | Priority | Status | Coverage
REQ-001 | Enforce valid status transitions | As a DAS user I want... | TC-001 | Given DRAFT contract When set ARCHIVED Then error | Critical | Approved | Full
Coverage summary
Total requirements
Requirements with test cases
Coverage %
Gaps / untested requirements
EXPECTED OUTPUTS
# | Output | Status | Owner | Uploaded to BAForge | Notes
1 | Traceability items (REQ > US > TC > Test Steps)
2 | Priority and status per trace
3 | Coverage analysis
ACTIONS & FOLLOW-UPS
# | Action | Owner | Due Date | Priority | Status | Linked Task | Notes
CONNECTED TASKS (cross-reference)
T03 | Requirements are the source
T06 | Rules refine requirements
T08 | Field requirements are traced
T20 | Traced requirements become Jira stories
SFL Consulting ¦ BAForge v3.1 ¦ Workshop Template

## T13 Risks
T27 Maintain Risk Register
Stage: Govern ¦ Step: Governance ¦ Category: Governance ¦ Tool: BAForge Agent > Governance > Risks
Goal: Identify, score (probability x impact), mitigate, and track project risks
WORKSHOP LOGISTICS
Date |  |  |  | Duration | 1-2 hours per review
Facilitator |  |  |  | Location / Link
Workshop Type | Risk review at each phase gate |  |  | Project
ATTENDEES
# | Name | Role | Organisation | Email | Present (Y/N) | Action Owner | Notes
1
2
3
4
5
6
PREPARATION CHECKLIST
# | Input Required | Source | Status | Owner | Notes
1 | Discovery findings (T02) |  | T02 output
2 | Compliance gaps (T04) |  | T04 output
3 | Open questions (T13) |  | T13 output
4 | Assumptions (T28) |  | T28 output
WORKSHOP CAPTURE
Risk identification
Risk ID | Description | Category | Prob (1-5) | Impact (1-5) | Score | Mitigation Plan | Owner
RSK-001 | FH API structure differs from ABAC flat files | Integration | 4 | 4 | 16 | Build adapter layer + validate mapping | Integration Lead
Risk scoring guide
Score interpretation | >=15 Critical (RED): Immediate escalation required 8-14 High (AMBER): Active mitigation, weekly review <=7 Low (GREEN): Monitor, monthly review
EXPECTED OUTPUTS
# | Output | Status | Owner | Uploaded to BAForge | Notes
1 | Risk register (RSK-001 to RSK-nnn)
2 | Probability x Impact score
3 | Mitigation plans
4 | Risk owners and status
5 | Linked requirements
ACTIONS & FOLLOW-UPS
# | Action | Owner | Due Date | Priority | Status | Linked Task | Notes
CONNECTED TASKS (cross-reference)
T02 | Discovery surfaces risks
T04 | Compliance gaps are regulatory risks
T13 | Unresolved questions are risks
T28 | Failed assumptions escalate to risks
T23 | Risk register exports to Excel
T12 | Risk mitigations feed deployment
SFL Consulting ¦ BAForge v3.1 ¦ Workshop Template

## T14 NFRs
T30 Define Non-Functional Requirements
Stage: Govern ¦ Step: NFRs & Sizing ¦ Category: Governance ¦ Tool: BAForge Agent > NFRs & Sizing > NFRs
Goal: Specify performance, availability, security, scalability, DR, and compliance targets
WORKSHOP LOGISTICS
Date |  |  |  | Duration | Half day
Facilitator |  |  |  | Location / Link
Workshop Type | NFR elicitation with architects + security + operations |  |  | Project
ATTENDEES
# | Name | Role | Organisation | Email | Present (Y/N) | Action Owner | Notes
1
2
3
4
5
6
PREPARATION CHECKLIST
# | Input Required | Source | Status | Owner | Notes
1 | Requirements (T03) |  | T03 output
2 | Compliance assessment (T04) |  | T04 output
3 | Data volumes (T31) |  | T31 output
4 | Existing SLAs |  | Operations team
WORKSHOP CAPTURE
NFR catalogue
NFR ID | Category | Requirement | Metric | Target | Measurement Method | Priority | Entity
NFR-001 | Performance | LCK pull must complete within 3s | Response time (p95) | < 3,000 ms | APM monitoring + load test | Critical | LCK
EXPECTED OUTPUTS
# | Output | Status | Owner | Uploaded to BAForge | Notes
1 | NFR catalogue (NFR-001 to NFR-nnn)
2 | Category, requirement, metric, target
3 | Measurement method
4 | Priority and linked entity
ACTIONS & FOLLOW-UPS
# | Action | Owner | Due Date | Priority | Status | Linked Task | Notes
CONNECTED TASKS (cross-reference)
T03 | Functional reqs have NFR counterparts
T04 | Compliance mandates specific NFRs
T11 | NFRs constrain tech specs
T31 | Volumes drive performance targets
T23 | NFRs export to Excel
SFL Consulting ¦ BAForge v3.1 ¦ Workshop Template

## T15 Volumes
T31 Estimate Data Volumes
Stage: Govern ¦ Step: NFRs & Sizing ¦ Category: Governance ¦ Tool: BAForge Agent > NFRs & Sizing > Data Volumes
Goal: Project data volumes, growth rates, concurrent users, API throughput, and storage per entity
WORKSHOP LOGISTICS
Date |  |  |  | Duration | 2-3 hours
Facilitator |  |  |  | Location / Link
Workshop Type | Sizing session with DBAs + architects |  |  | Project
ATTENDEES
# | Name | Role | Organisation | Email | Present (Y/N) | Action Owner | Notes
1
2
3
4
5
6
PREPARATION CHECKLIST
# | Input Required | Source | Status | Owner | Notes
1 | Data model entities (T08) |  | T08 output
2 | Production database stats |  | DBA team
3 | Business growth projections |  | Business planning
WORKSHOP CAPTURE
Data volume estimates
Entity | Current Rows | Growth %/yr | Projected Go-Live | Peak Users | API Calls/Min | Avg Record KB | SLA Target
Legal Commitments (LCK) | 12,000 | 8% | 12,960 | 200 | 50 | 4.2 KB | < 3s (EP01)
Infrastructure sizing
Total storage estimate | Sum of (projected rows x record size) across all entities
Database sizing | Primary + replica + backup retention requirements
Network bandwidth | Peak API traffic x average payload size
Scaling strategy | Horizontal / vertical / auto-scaling thresholds
EXPECTED OUTPUTS
# | Output | Status | Owner | Uploaded to BAForge | Notes
1 | Per entity: current rows, growth %, projected volume
2 | Peak concurrent users
3 | API calls/min at peak
4 | Record size and total storage
5 | SLA targets per entity
ACTIONS & FOLLOW-UPS
# | Action | Owner | Due Date | Priority | Status | Linked Task | Notes
CONNECTED TASKS (cross-reference)
T08 | Entities drive volume estimation
T10 | API call volumes feed endpoint sizing
T11 | Volumes drive infrastructure decisions
T12 | Volumes drive cutover planning
T30 | Volumes drive NFR targets
T23 | Volumes export to Excel with formulas
SFL Consulting ¦ BAForge v3.1 ¦ Workshop Template

## Export Actors
Export: Actors
Copy rows 5-16, paste into BAForge Agent > Business Logic > Actors > Import CSV
Source: T05 Actors (rows 29+) ¦ BAForge CSV layout: actors ¦ Copy rows 5:16 → paste into BAForge CSV import
ID | Name | Type | Description | CRUD | Permissions
COLUMN MAPPING
CSV Column | Source | Description
ID | 'T05 Actors'!A | Actor identifier (AC001 format)
Name | 'T05 Actors'!B | Actor display name
Type | 'T05 Actors'!C | Primary Actor / Secondary Actor / System Actor / External System / Timer/Scheduler
Description | 'T05 Actors'!D | Role description
CRUD | Formula: ='T05 Actors'!E{r}&IF('T05 Actors'!F{r}="Y","R","")&IF('T05 Actors'!G{r}="Y","U","")&IF('T05 Actors'!H{r}="Y","D","") | Concatenated CRUD string from individual C/R/U/D columns
Permissions | Manual entry | Manual: permission scope description

## Export Rules
Export: Rules
Copy rows 5-21, paste into BAForge Agent > Business Logic > Rules > Import CSV
Source: T06 Rules (rows 29+) ¦ BAForge CSV layout: rules ¦ Copy rows 5:21 → paste into BAForge CSV import
ID | Name | Category | Priority | Condition | Action | Exception | Source | RelatedReq
COLUMN MAPPING
CSV Column | Source | Description
ID | 'T06 Rules'!A | Rule ID (BR001 format)
Name | 'T06 Rules'!B | Rule name
Category | 'T06 Rules'!C | Validation / Calculation / Authorization / Workflow / Data Quality / Compliance / Integration / Notification
Priority | 'T06 Rules'!D | Critical / High / Medium / Low
Condition | 'T06 Rules'!E | IF condition
Action | 'T06 Rules'!F | THEN action
Exception | 'T06 Rules'!G | ELSE exception
Source | 'T06 Rules'!H | Source document or regulation
RelatedReq | Manual entry | Manual: linked requirement ID (REQ-XXX)

## Export Workflows
Export: Workflows
Copy rows 5-22, paste into BAForge Agent > Business Logic > Workflows > Import CSV. Note: WF_ID/Name/Trigger/Owner repeat for every step row.
Source: T07 Workflows (rows 36+) ¦ BAForge CSV layout: workflows ¦ Copy rows 5:22 → paste into BAForge CSV import
WF_ID | Name | Trigger | Owner | Step_Num | Step_Type | Step_Description | Step_Actor | Step_Output
COLUMN MAPPING
CSV Column | Source | Description
WF_ID | 'T07 Workflows'!='T07 Workflows'!B27 | From workflow header (same for all steps in this WF)
Name | 'T07 Workflows'!='T07 Workflows'!B28 | From workflow header Name field
Trigger | 'T07 Workflows'!='T07 Workflows'!B29 | From workflow header Trigger field
Owner | 'T07 Workflows'!='T07 Workflows'!B30 | From workflow header Owner field
Step_Num | 'T07 Workflows'!A | Step number from steps table
Step_Type | 'T07 Workflows'!B | Action / Decision / Subprocess / Start / End
Step_Description | 'T07 Workflows'!C | Step description
Step_Actor | 'T07 Workflows'!D | Actor performing this step
Step_Output | Manual entry | Manual: step output — or use column F if captured

## Export Fields
Export: Fields
Copy rows 5-26, paste into BAForge Agent > Data Model > (select entity) > Import CSV: Fields
Source: T08 DataModel (rows 35+) ¦ BAForge CSV layout: fields ¦ Copy rows 5:26 → paste into BAForge CSV import
Field_Name | Label | Source_Path | Target_Field | Data_Type | Edit_Mode | Mandatory | BR_Ref | Sample_Value | Migration_Status | Compliance_Note
COLUMN MAPPING
CSV Column | Source | Description
Field_Name | 'T08 DataModel'!A | Technical field name
Label | 'T08 DataModel'!B | Display label
Source_Path | 'T08 DataModel'!C | Source system path (e.g. api.response.field)
Target_Field | 'T08 DataModel'!D | Target system field name
Data_Type | 'T08 DataModel'!E | String / Integer / Decimal / Boolean / Date / DateTime / Array / Object / Enum
Edit_Mode | 'T08 DataModel'!F | Read / Edit / Auto / System / Calculated
Mandatory | 'T08 DataModel'!G | Y or N
Migration_Status | 'T08 DataModel'!H | ok / TBI / Gap / N/A / Partial / Deprecated
Sample_Value | Manual entry | Manual: example value for this field
BR_Ref | Manual entry | Manual: business rule reference (BR053)
Compliance_Note | Manual entry | Manual: GDPR / regulatory note

## Export Endpoints
Export: Endpoints
One row per endpoint. For multiple endpoints, fill one workshop sheet per EP, or consolidate manually here.
Source: T09 APIs (rows 28+) ¦ BAForge CSV layout: apiEndpoints ¦ Copy rows 5:12 → paste into BAForge CSV import
ID | Method | Path | Description | Entity | Call_Sequence | Rate_Limiting | Request_Sample | Response_Sample
COLUMN MAPPING
CSV Column | Source | Description
ID | 'T09 APIs'!B | Endpoint ID from workshop capture
Method | 'T09 APIs'!='T09 APIs'!B29 | HTTP method
Path | 'T09 APIs'!='T09 APIs'!B30 | API path
Description | 'T09 APIs'!='T09 APIs'!B31 | Endpoint description
Entity | 'T09 APIs'!='T09 APIs'!B32 | Related entity
Call_Sequence | Manual entry | Manual: copy from workshop call sequence field
Rate_Limiting | 'T09 APIs'!='T09 APIs'!B34 | Rate limiting info
Request_Sample | Manual entry | Manual: JSON request sample
Response_Sample | Manual entry | Manual: JSON response sample

## Export Requirements
Export: Requirements
Pulls REQ ID, text, and priority from T03 requirements table. Add user stories and test cases manually, then import into BAForge > Traceability.
Source: T03 To-Be (rows 33+) ¦ BAForge CSV layout: traceability ¦ Copy rows 5:18 → paste into BAForge CSV import
Req_ID | Requirement | User_Story | Test_Case | Test_Steps | Priority | Status
COLUMN MAPPING
CSV Column | Source | Description
Req_ID | 'T03 To-Be'!A | Requirement ID (REQ-001 format)
Requirement | 'T03 To-Be'!B | Requirement statement
User_Story | Manual entry | Manual: As a [role] I want [capability] so that [benefit]
Test_Case | Manual entry | Manual: Test case ID (TC-001)
Test_Steps | Manual entry | Manual: Given/When/Then steps
Priority | 'T03 To-Be'!C | Critical / High / Medium / Low — from workshop priority column
Status | Manual entry | Manual: Draft / Approved / In Progress / Implemented / Tested

## Export Questions
Export: Questions
Open questions emerge from multiple workshops (T02 discovery, T04 compliance, T08 data model TBI fields). Fill manually from workshop action items.
Source: T08 DataModel (rows 35+) ¦ BAForge CSV layout: openQuestions ¦ Copy rows 5:16 → paste into BAForge CSV import
ID | Question | Context | Entity_Field | Priority | Status | Assigned_To | Answer
COLUMN MAPPING
CSV Column | Source | Description
ID | Manual entry | Manual: Q001 format
Question | Manual entry | Manual: the question text
Context | Manual entry | Manual: why this question matters
Entity_Field | Manual entry | Manual: Entity.field reference (e.g. LCK.notice_period)
Priority | Manual entry | Critical / High / Medium / Low
Status | Manual entry | Open / In Progress / Answered / Blocked / Closed
Assigned_To | Manual entry | Manual: who should answer this
Answer | Manual entry | Manual: resolution when answered

## Export Glossary
Export: Glossary
Glossary terms emerge from all workshops. Collect terms as they come up, define in this sheet, import into BAForge > Open Items > Glossary.
Source: T08 DataModel (rows 35+) ¦ BAForge CSV layout: glossary ¦ Copy rows 5:24 → paste into BAForge CSV import
Term | Definition | Related_Entity
COLUMN MAPPING
CSV Column | Source
Term | Manual entry | Manual: domain term or acronym
Definition | Manual entry | Manual: clear definition
Related_Entity | Manual entry | Manual: linked entity name (LCK, LEF, BAF)

## Export Risks
Export: Risks
Pulls risk data from T13 capture table. Score is calculated in BAForge (prob x impact). Import via agent Governance > Risks.
Source: T13 Risks (rows 29+) ¦ BAForge CSV layout: risks ¦ Copy rows 5:18 → paste into BAForge CSV import
Risk_ID | Description | Category | Probability | Impact | Mitigation | Owner | Status | Linked_REQ
COLUMN MAPPING
CSV Column | Source | Description
Risk_ID | 'T13 Risks'!A | Risk ID (RSK-001 format)
Description | 'T13 Risks'!B | Risk description
Category | 'T13 Risks'!C | Technical / Operational / Regulatory / Financial / Organisational / External / Data Quality / Integration
Probability | 'T13 Risks'!D | 1-5 scale
Impact | 'T13 Risks'!E | 1-5 scale
Mitigation | 'T13 Risks'!G | Mitigation plan — column G (skips Score formula in F)
Owner | 'T13 Risks'!H | Risk owner
Status | Manual entry | Manual: Open / Mitigating / Accepted / Closed / Escalated
Linked_REQ | Manual entry | Manual: linked requirement (REQ-XXX)

## Export NFRs
Export: NFRs
Direct pull from T14 NFR catalogue. Import into BAForge > NFRs & Sizing > Non-Functional Reqs.
Source: T14 NFRs (rows 29+) ¦ BAForge CSV layout: nfrs ¦ Copy rows 5:18 → paste into BAForge CSV import
NFR_ID | Category | Requirement | Metric | Target | Measurement_Method | Priority | Linked_Entity
COLUMN MAPPING
CSV Column | Source | Description
NFR_ID | 'T14 NFRs'!A | NFR ID (NFR-001 format)
Category | 'T14 NFRs'!B | Performance / Availability / Security / Scalability / DR / Usability / Maintainability / Compliance
Requirement | 'T14 NFRs'!C | NFR statement
Metric | 'T14 NFRs'!D | Measurable metric
Target | 'T14 NFRs'!E | Target value
Measurement_Method | 'T14 NFRs'!F | How to verify
Priority | 'T14 NFRs'!G | Critical / High / Medium / Low
Linked_Entity | 'T14 NFRs'!H | Related entity

## Export Volumes
Export: Volumes
Direct pull from T15 data volume table. Projected volume is auto-calculated in BAForge. Import into BAForge > NFRs & Sizing > Data Volumes.
Source: T15 Volumes (rows 28+) ¦ BAForge CSV layout: dataVolumes ¦ Copy rows 5:16 → paste into BAForge CSV import
Entity | Current_Rows | Growth_Pct | Peak_Users | API_Calls_Min | Record_Size_KB | SLA_Target
COLUMN MAPPING
CSV Column | Source | Description
Entity | 'T15 Volumes'!A | Entity name
Current_Rows | 'T15 Volumes'!B | Current row count
Growth_Pct | 'T15 Volumes'!C | Annual growth percentage
Peak_Users | 'T15 Volumes'!E | Peak concurrent users
API_Calls_Min | 'T15 Volumes'!F | API calls per minute at peak
Record_Size_KB | 'T15 Volumes'!G | Average record size in KB
SLA_Target | 'T15 Volumes'!H | SLA target for this entity